**Додаток (Appendix) 2**до тендерної документації

(to the Bidding documents)

|  |  |
| --- | --- |
| **ДОГОВОР**  на виконання робіт з проєктування та будівництва  м. Київ "\_\_\_\_" \_\_\_\_\_\_\_\_\_\_\_ 2023  **Державна митна служба України** у подальшому іменована як **Замовник,** в особі **в. о. Голови Держмитслужби Сергія Звягінцева**, який діє на підставі Положення про Державну митну службу України, затвердженого постановою Кабінету Міністрів України від 6 березня 2019 року № 227 та, з однієї сторони,  та **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**  **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_,** яке створене та діє відповідно до законодавства Республіки Польща, зареєстроване \_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_,в особі **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**,іменована як **Виконавець**  за результатами здійснення процедури закупівлі «\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_», у відповідності до умов Договору між Урядом України та Урядом Республіка Польща про надання кредиту на умовах пов’язаної допомоги від 09.09.2015 (Договір ратифіковано Законом України № 977-VIII від 03.02.2016) та постанови Кабінету Міністрів України «Деякі питання реалізації Договору між Урядом України та Урядом Республіки Польща про надання кредиту на умовах пов’язаної допомоги» від 14.02.2017 № 73 (зі змінами), згідно з якою відповідальним виконавцем за відповідною бюджетною програмою є Державна митна служба України, уклали Договір такого змісту:  **1. Предмет Договору**  1.1. Виконавець зобов'язується у порядку та на умовах, визначених цим Договором своїми силами і засобами, зазначеними в Переліку механізмів, машин та обладнання (Додаток 13), що є частиною Договору, на власний ризик та/або із залученням субпідрядних організацій виконати та здати в установлений цим Договором термін завершені роботи з Реконструкції міжнародного пункту пропуску для автомобільного сполучення «Шегині», на українсько-польському кордоні за моделлю «проектування та будівництво».  1.2. Найменування об’єкту: роботи з **«Реконструкції міжнародного пункту пропуску для автомобільного сполучення «Шегині» на українсько-польському кордоні» за моделлю «проектування та будівництво»**.  1.3. Замовник повинен передати Виконавцю територію будівництва за місяць до дня початку будівельних робіт за вимогою Виконавця. Передача території будівництва має відбутися на підставі Акту передання будівельного майданчика (Додаток 11). До моменту передачі будівельного майданчику, Замовник зобов’язується забезпечити доступ Виконавця до об’єкту, для виконання обмірних креслень існуючої інфраструктури пункту пропуску та актів обстеження їх технічного стану.  1.4. Адреса розташування місця виконання предмету замовлення: Міжнародний пункт пропуску для автомобільного сполучення «Шегині», Львівська область, Яворівський р-н, вул. Дружби, 201.  1.5. Предметний обсяг робіт складають проєктні роботи і будівельні роботи, обсяг яких визначено проєктною документацією.  1.6. Обсяг будівельних робіт може бути змінений Замовником в інтересах виконання проєкту, в тому числі у разі необхідності виконання додаткових робіт, які не враховані проєктом, проте необхідні для введення обєкта в експлуатацію, покращення предмета замовлення (закупівлі) та нерозривно повязані із предметом замовлення (закупівлі). Додатковий обсяг робіт виконується в межіх договірної ціни за рахунок коштів на покриття ризиків, врахованих у договірній ціні після коригування проєкту шляхом внесення змін до договору  **2. Термін виконання**  2.1. Сторони постановили, що предмет Договору має бути виконаний протягом \_\_\_\_ (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_) календарних місяців з дати укладання цього Договору у відповідності до процедури передбаченої умовами Договору між Урядом України та Урядом Республіка Польща про надання кредиту на умовах пов’язаної допомоги від 09 вересня 2015 року, та пунктом 16.2 даного Договору, в тому числі:  2.1.1. Підготовчі роботи на ділянці виїзду з України (перший пусковий комплекс): \_\_\_\_\_\_ (\_\_\_\_\_\_\_) місяців з дати отримання дозволу на виконання будівельних робіт та передання будівельного майданчика;  2.1.2. Реконструкція ділянки виїзду з України (перший пусковий комплекс): \_\_\_\_\_\_ (\_\_\_\_\_\_\_);  2.1.3. Введення ділянки виїзду з України (перший пусковий комплекс) в експлуатацію: протягом \_\_\_\_\_ (\_\_\_\_\_\_) місяців;  2.1.4. Підготовчі роботи на ділянці в’їзду в Україну (другий пусковий комплекс) \_\_\_\_\_\_ (\_\_\_\_\_\_\_) місяців з дати передання будівельного майданчика;  2.1.5. Реконструкція ділянки в’їзду в Україну (другий пусковий комплекс): \_\_\_\_\_\_ (\_\_\_\_\_\_\_) ;  2.1.6. Введення ділянки в’їзду в Україну (другий пусковий комплекс) в експлуатацію: протягом \_\_\_\_\_ (\_\_\_\_\_\_) місяців;  2.2. Сторони погодили, що строки виконання робіт (етапів робіт) продовжуються на строк неможливості виконання робіт (вище вказаних етапів робіт) з причин, що не залежать від Виконавця, такі як (але не обмежуючись) – затримка отримання Дозволу на виконання будівельних робіт Замовником, затримка передання будівельного майданчика тощо. Про випадки затримки виконання робіт (етапів робіт) з причин незалежних від Виконавця, останній негайно (не більше п’яти робочих днів від дня виникнення відповідних обставин) повідомляє Замовника.  2.3. Датою завершення предмету Договору вважається дата введення об’єкта в експлуатацію відповідно до вимог Порядку прийняття в експлуатацію закінчених будівельних об’єктів затверджений постановою Кабінету Міністрів України від 13 квітня 2011 року № 461.  **3. Договірна ціна**  3.1. За виконання предмету Договору Виконавцю виплачуються кошти у розмірі \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_), за умови, що вартість матеріалів, обладнання, робіт та послуг польського походження не м оже бути меншою ніж 60 % (шістдесят відсотків) від вартості цього Договору.  Для цілей цього Договору та відповідно до статті 11 Договору між Урядом України та Урядом Республіки Польща про надання кредиту на умовах пов’язаної допомоги, вчиненого 09 вересня 2015 року у м. Варшаві, операції з ввезення на митну територію України товарів та/або постачання на митній території України товарів/робіт/послуг виконавцем цього Договору – резидентом Республіки Польща виключно для реалізації цього Договору звільняються від оподаткування податком на додану вартість згідно з національним законодавством України навіть, якщо на митній території Республіки Польща до цих же товарів/робіт/послуг застосовувалася ставка ПДВ «0» відповідно до національного законодавства Республіки Польща.  3.1.1. Відшкодування вартості робіт з виготовлення робочих креслень, робочої документації, коригування проєкту, авторського нагляду тощо \_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.1.2. Підготовчі роботи на ділянці виїзду з України (перший пусковий комплекс) – \_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_), включаючи: вартість матеріалів та обладнання – \_\_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_) та вартість робіт та послуг – \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.1.3. Реконструкція ділянки виїзду з України (перший пусковий комплекс) – \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_), включаючи: вартість матеріалів та обладнання – \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_) та вартість робіт та послуг – \_\_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.1.4. Введення ділянки виїзду з України (перший пусковий комплекс) в експлуатацію – \_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.1.5. Підготовчі роботи на ділянці в’їзду в Україну (другий пусковий комплекс) – \_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_),включаючи: вартість матеріалів та обладнання – \_\_\_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_) та вартість робіт та послуг – \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.1.6. Реконструкція ділянки в’їзду в Україну (другий пусковий комплекс) – \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_), включаючи: вартість матеріалів та обладнання – \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_) та вартість робіт та послуг – \_\_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.1.7. Введення ділянки в’їзду з України (другий пусковий комплекс) в експлуатацію – \_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.2. Виконавець виконує роботи зі своїх матеріалів, своїми засобами та обладнанням, вартість яких визначається Договірною ціною в ЄВРО (додаток - 2) в тому числі з Договірною ціною на будівництво (додаток 2.1). Договірна ціна є твердою.  При цьому Виконавець може через своє постійне представництво ввезти необхідні матеріали та обладнання на митну територію України в цілях виконання робіт за цим Договором та здійснити їх митне оформлення безпосередньо у місці виконання робіт, а саме в міжнародному пункті пропуску «Шегині» Львівської митниці.  Всі експортні документи, в першу чергу рахунки-фактури, повинні включати положення «за Договором між Урядом України та Урядом Республіки Польща про надання кредиту на умовах пов’язаної допомоги від 09.09.2015».  3.3. Джерело фінансування 100% кредитних коштів, отриманих відповідно до Договору між Урядом України та Урядом Республіка Польща про надання кредиту на умовах пов’язаної допомоги від 09.09.2015 (далі – Кредит).  Будь-які податки, збори та інші платежі, які можуть виникнути у зв’язку з виконанням даного Договору, сплачуються кожною стороною Договору у її відповідній країні і не фінансуються за рахунок Кредиту. Товари, роботи та послуги, що фінансуються відповідно до даного Договору, звільняються від сплати будь-яких податків, митних чи інших зборів або обов’язкових платежів, які встановлені Україною чи на її території у відповідності до чинного законодавства України.  3.4. Оплата, про яку йдеться, охоплює комплексне виконання предмету даного договору, вказаного у розділі 1, а також усіх робіт і дій, від яких залежить проходження експертизи проєкту, отримання дозволу на виконання будівельних робіт та сертифікату, що підтверджує готовність об’єкту до експлуатації, а також інших документів, необхідних для кінцевого прийняття предмету Договору.  Оплата, про яку йдеться у пункті 3.1 даного Договору, залишається незмінною до кінця виконання предмету Договору.  3.5. Ціна Договору може бути змінена, у тому числі у бік збільшення, з урахуванням змін ринкових цін на товари в країнах Сторін у період виконання Договору. Зміна вартості Договору здійснюється виключно в частині незавершених та додаткових робіт за наявності позитивного експертного звіту за результатами коригування проектної документації, виданого у встановленому українським законодавством порядку. Зміни до Договору погоджуються Договірними Сторонами у передбаченому пунктом 4 статті 3 Договору між Урядом України та Урядом Республіка Польща про надання кредиту на умовах пов’язаної допомоги від 09.09.2015.  **4. Субпідряд**  4.1. Виконавець має право за згодою Замовника залучати до виконання договору Субпідрядників, на умовах укладених з ними субпідрядних договорів.  Разом з ти, Виконавець під час вибору субпідрядника повинен врахувати норми:  - Закону України «Про санкції» від 14.08.2014 № 1644-VII, та іншими нормативно-правовими актами прийнятими на його підставі;  - постанови Кабінету Міністрів України «Про забезпечення захисту національних інтересів за майбутніми позовами держави Україна у зв’язку з військовою агресією Російської Федерації» від 3.03.2022 № 187, оскільки замовник не може виконувати зобов’язання, кредиторами за якими Російська Федерація або особи пов’язані з країною агресором, що визначені пунктом 1 пункту 1 вказаної Постанови;  - постанови Кабінету Міністрів України «Про застосування заборони ввезення товарів з Російської Федерації» від 09.04.2022 № 426;  - Закону України «Про забезпечення прав і свобод громадян та правовий режим на тимчасово окупованій території України» від 15.04.2014 № 1207-VII.  4.2. Замовник має право відмовити Виконавцю у залученні конкретного Субпідрядника у разі, якщо кандидатура Субпідрядника не відповідає вимогам, зазначеними у пункті 4.1.  4.3. Виконавець має право залучати суб’єктів господарювання – резидентів України до виконання робіт в обсягах не більше 40% вартості Договору.  4.4. Виконавець за необхідності може залучати до виконання будівельних робіт суб’єктів господарювання - нерезидентів України.  4.5. Виконавець відповідає за дії або бездіяльність Субпідрядника, його представників або працівників, як за власні дії або бездіяльність.  4.6. Договір між Виконавцем і Субпідрядником не може суперечити положенням даного Договору.  4.7. Термін виконання робіт Субпідрядником повинен відповідати терміну виконання предмету Договору, укладеного між Замовником і Виконавцем, та хронології робіт, які є предметом Договору, обумовлених технологічним процесом, принципам будівельної науки.  4.8. Договір субпідряду не може містити положень, які передбачають залежність між отриманням субпідрядником платежу від Виконавця та отриманням Виконавцем оплати за обсяг робіт, виконаних субпідрядником.  4.9. Виконавець зобов’язаний представити Замовнику Кандидатуру Субпідрядника, разом з вказанням предмету договору субпідряду, реквізитами Субпідрядника, відповідальними особами Субпідрядника не пізніше, ніж за 14 днів до запланованого терміну укладення договору субпідряду.  4.10. Датою представлення кандидатури Субпідрядника Замовнику вважається дата подання офіційного листа Виконавця в канцелярію Замовника або на його офіційну електронну адресу: post@customs.gov.ua.  4.11. Замовник протягом 14 днів з дати надходження офіційного листа з представленням кандидатури Субпідрядника повинен надати письмове погодження кандидатури Субпідрядника, або його письмове заперечення з наданням обґрунтованого пояснення.  4.12. Кандидатура субпідрядника, вважається погодженою після отримання письмового погодження від Замовника.  У разі відсутності такого погодження чи заперечення після закінчення строку, визначеного пунктом 4.11. Договору, кандидатура Субпідрядника вважається погодженою.  4.13. Доручення виконання завдання іншому субпідряднику, ніж той, який був погоджений, допускається за погодженням із Замовником, як це визначено у пункті 4.9. Договору.  **5. Умови виконання робіт**  5.1. Виконавець заявляє, що він ознайомився з умовами виконання предмету даного Договору та врахував їх при визначенні договірної ціни за даним договором та терміну виконання предмету даного Договору.  5.2. Виконавець заявляє, що він ознайомився з умовами, які повинні бути враховані при виконанні і прийнятті робіт. Виконавець заявляє, що у випадку виявлення помилок або невідповідностей у процесі виконання робіт, допущених з його вини, він усуне їх власними силами, не змінюючи суму договірної ціни і терміни виконання, передбачені даним договором. Усі зміни у обсягах будівельних робіт, відмінних від затвердженої Замовником проєктної документації, а також усі додаткові роботи, що виникнуть не з вини Виконавця, будуть виконуватись Виконавцем лише після узгодження з Замовником строку їх виконання та вартості за результатами коригування та експертизи вартості таких робіт, за рахунок вартості ризиків, врахованих в розрахунку Договірної ціни.  5.3. Виконавець зобов'язаний виконати предмет Договору згідно з проєктною документацією, будівельною наукою, чинним законодавством України, іншими діючими нормативними документами України, пов'язаними з предметом Договору.  5.4. Виконавець зобов’язаний виконати/замовити розробку робочої документації, коригування проєкту за необхідності, та відшкодувати власнику немайнових прав твору архітектури здійснення авторського нагляду в межах вартості таких робіт передбачених затвердженим проєктом будівництва. Вартість зазначених робіт включено до Договірної ціни відповідно до Розділу 3 договору.  5.5. Виконавець гарантує, що перед початком підготовчих та будівельних робіт передасть Замовнику повний комплект робочої документації у паперовому вигляді в 2 (двох) примірниках та в електронному вигляді 1 (один) екземпляр, включаючи всі креслення у форматі dwg, а текстові – pdf та doc, розробленої у відповідності до чинного законодавства України та з урахуванням наявного та затвердженого проєкту будівництва.  5.6. Виконавець зобов'язаний виконати роботи відповідно до обсягу замовлення та із врахуванням погоджених із Замовником змінених робіт, якщо такі можуть виникнути відповідно до п.1.6. договору.  5.7. Виконавець зобов'язується виконати предмет Договору з власних матеріалів (або матеріалів субпідрядника). Матеріали, використані для виконання предмету даного Договору, повинні мати належні сертифікати, допуски і свідоцтва, передбачені чинним законодавством, відповідати технічним умовам проєктування, виконання і прийняття робіт. Усі товари, які експортуються з Республіки Польща до України за цим Договором між Урядом України та Урядом Республіки Польща про надання кредиту на умовах пов’язаної допомоги, не можуть бути ре-експортовані до третіх країн без письмового дозволу Міністра фінансів Республіки Польща. Вартість товарів, робіт та послуг польського походження за Договором, який фінансується за Договором між Урядом України та Урядом Республіки Польща про надання кредиту на умовах пов’язаної допомоги, не може бути меншою, ніж 60% (шістдесят відсотків) від вартості цього Договору. Детальна інформація про виконання цієї вимоги, включаючи надання відповідних документів, наприклад сертифікатів про походження, може вимагатись від Виконавця Урядом Республіки Польща.  5.8. У процесі виконання предмету договору Виконавець зобов'язаний дотримуватися правил техніки безпеки, виробничої санітарії і протипожежного захисту.  5.9. Виконавець вважається відповідальним за територію виконання будівельних робіт з моменту її прийняття від Замовника до моменту виконання і передачі предмету Договору в експлуатацію та несе відповідальність за можливі збитки, що виникають з вини Виконавця.  5.10. Виконавець зобов'язаний забезпечити охорону території виконання робіт, у тому числі усіх матеріалів і пристроїв, що там знаходяться.  5.11. Усі будівельні відходи, наприклад, сміття, демонтовані матеріали і пристрої, мають бути вивезені за межі території будівництва та утилізовані. Будівельні відходи мають вивозитися у поточному режимі. Складування будівельних відходів на території виконання робіт заборонене.  5.12. Відповідно до своїх потреб Замовник має право скликати координаційні наради, повідомляючи про це Виконавця у поточному режимі, натомість Виконавець зобов'язаний брати в них участь.  5.13. Після завершення робіт Виконавець зобов'язаний привести територію, зайняту ним під час виконання будівельних робіт (постійно або тимчасово), у вихідний стан, зокрема відновити та очистити дороги, тротуари, зелені насадження тощо.  5.14. Аспекти та питання, не врегульовані у наведених правилах виконання робіт, підлягають погодженню у поточному режимі на етапі виконання будівельних робіт.  **6. Обов’язки Замовника**  6.1. Замовник зобов’язується:  6.1.1. Передати Підряднику проектно - кошторисну документацію згідно з Актом прийому-передачі технічної документації (Додаток 12).  6.1.2. Передати Виконавцю територію виконання робіт та скласти відповідний акт згідно з п. 1.3 даного договору.  6.1.3. Не перешкоджати доступу Підрядника до місця виконання підрядних робіт;  6.1.4. Вказати місця підключення до мереж електропостачання і водопостачання.  6.1.6. Провести приймання робіт на умовах, передбачених цим Договором та законодавством України.  6.2. При виявленні Замовником порушень умов Договору щодо якості, вартості, обсягів та строків виконання робіт, у т. ч. матеріальних ресурсів, Замовник інформує про такі порушення Виконавця шляхом направлення на його електронну адресу відповідного припису, який є обов’язковим для розгляду протягом 5 (п’яти) робочих днів і у разі не надання Виконавцем протягом 2 (двох) календарних днів з дня отримання на електронну адресу заперечень, вважається прийнятим до виконання, а зазначені у приписі дефекти усуваються протягом 14-ти (чотирнадцяти) календарних днів з дня отримання припису, про що Виконавець повідомляє Замовника листом- повідомленням на електронну адресу.  **7. Обов’язки Виконавця**  7.1. Виконавець зобов'язується:  7.1.1. Прийняти територію виконання робіт;  7.1.2. Підтримувати порядок на території виконання робіт шляхом, зокрема:  7.1.2.1. забезпечення охорони території будівництва і майна;  7.1.2.2. забезпечення протипожежного захисту;  7.1.2.3. здійснення нагляду за технікою безпеки і виробничою санітарією;  7.1.2.4. недопущення транспортних перешкод на території виконання робіт, усування аварій, пов’язаних з будівництвом.  7.1.2.5. позначення і маркування території, встановлення тимчасової огорожі.  7.1.3. Виконавець несе відповідальність перед третіми особами за усі збитки, спричинені виконанням робіт.  7.1.4. Забезпечити належну організацію і координацію робіт шляхом забезпечення відповідного керівництва.  7.1.6. Детально перевірити умови на місцевості виконання замовлення.  7.1.7. Надати в строк не більше 20-ти робочих днів з дати набрання чинності цим Договором та погодити із Замовником поетапний графік виконання будівельних робіт. При порушенні Виконавцем з його вини строків, визначених у розділі 2 Договору та неусунені таких прострочень для забезпечення належного та повного виконання предмету договору, що зумовить порушення кінцевого терміну завершення робіт, таке порушення Договору визнається Сторонами як невиконання істотної умови Договору і є підставою для розірвання Договору Замовником в односторонньому порядку.  7.1.8. Спільно із Замовником отримати дозвіл на виконання будівельних робіт в органах державного архітектурно-будівельного контролю, на будівництво і виконання будівельних робіт у частині, що відповідає предмету даного Договору 7.1.9. Розпочати виконання робіт в строк, зазначений в графіку виконання робіт, про що письмово повідомити Замовника шляхом направлення відповідного листа- повідомлення на електронну адресу Замовника та поштовим зв’язком.  7.1.10. Направляти на електронну адресу Замовника звіт про виконану протягом 14 календарних днів роботу, а саме: об’єми та види виконаних робіт, двічі, протягом поточного місяця - 15-го і 30-го числа, а у випадку вихідних днів - на наступний робочий день, не пізніше 18.00 год.  7.1.11. Організувати територію будівництва, зокрема, забезпечити транспортне сполучення, огорожу, підведення мереж, тимчасові об’єкти та вчинення усіх інших дій, необхідних для належного виконання робіт. Виконавець зобов’язаний забезпечити захист і маркування виконуваних робіт та дбати про технічний стан і правильність маркування протягом усього часу виконання будівельних робіт, забезпечити безперервність і безпеку проїзду через пропускний пункт, тротуарах і автостоянках, розташованих навколо території будівництва, які використовуються або перетинаються Виконавцем у процесі виконання робіт, а також отримати усі необхідні для цього погодження і дозволи.  7.1.12. Виконувати і виконати будівельні роботи згідно з чинними положеннями законодавства України, правилами техніки безпеки і виробничої санітарії.  7.1.13. Співпрацювати зі службами Замовника та підприємства (організації), яке здійснюватиме консультаційні послуги щодо супроводження проєкту будівництва Інженером, залученим Замовником у порядку, передбаченому п.15.1. Договору (далі – Інженер).  7.1.14. Вести журнал виконання будівельних робіт.  7.1.15. Забезпечити кадри і контроль за наявністю відповідних повноважень.  7.1.16. Забезпечити наявність обладнання, що відповідає вимогам технічних стандартів.  7.1.17. Надати Замовнику та Інженеру сертифікати, свідоцтва і технічні допуски на використані матеріали та арматуру, гарантійні талони на встановлені пристрої не пізніше, ніж в день кінцевого прийняття робіт.  7.1.18. У письмовій формі повідомляти Замовника та Інженера про заплановані прийняття робіт.  7.1.19. Прибрати будівельний майданчик і передати територію Замовнику не пізніше 14 робочих днів з дня підписання сторонами акту кінцевого прийняття робіт.  7.1.20. Виконавець оплачує усі витрати, пов’язані з виконанням покладених на нього обов’язків.  7.1.21. Згідно з правилами, що стосуються небезпечних речовин, Виконавець зобов’язується усувати усі поставлені на територію виконання робіт небезпечні речовини разом з тарою або упаковкою. Витрати на усунення цих речовин разом з тарою або упаковкою покладаються на Виконавця.  7.1.22. Створити електронний кабінет учасника будівництва на порталі Єдиної державної електронної системи у сфері будівництва з метою:  1) створення, завантаження та підписання документів;  2) внесення відомостей про укладені договори підряду, інформації про відповідального виконавця робіт, який закріплений підрядником за відповідним об’єктом будівництва;  3) підтвердження залучення до виконання робіт (послуг), пов’язаних із створенням об’єктів архітектури;  4) підтвердження відомостей про документи, що створювалися до запровадження електронної системи;  5) листування з користувачами електронної системи, держателем та технічним адміністратором;  6) створення та підписання акта про демонтаж.  7.2. Виконавцю забороняється:  7.2.1. Складувати безпосередньо на землі відходи, що утворилися в результаті виконаних робіт, а також бетон і розчини.  7.2.2. Завозити на територію Замовника будь-які відходи.  7.2.3. Складувати речовини, які можуть забруднити воду, ґрунт, атмосферне повітря, натомість у випадку використання цих речовин для виконання робіт деталі їхнього складування і використання мають бути погоджені з особами, відповідальними за охорону довкілля.  7.2.4. Мити транспортні засоби і обладнання на території виконання робіт.  7.2.5. Спалювати відходи.  **8. Проєктування і авторський нагляд**  8.1. Розробка робочої документації здійснюється за замовленням Виконавця коригування проєктної документації та авторський нагляд за здійсненням будівельно-монтажних робіт здійснюються власником немайнових прав на твір архітектури - розробником затвердженого проекту або уповноваженими ним особами.  8.2. Виконавець замовляє розробку робочої документації, коригування проєкту за необхідності, здійснення авторського нагляду в межах вартості таких робіт передбачених, затвердженим проєктом будівництва.  8.3. Виконавець повинен включити в договір щодо розробки робочої документації та коригування проєкту всі положення цього договору, включаючи відповідні гарантії і вимоги.  8.4. Всі зміни до затвердженого проєкту будівництва вносяться з відома і погодження Замовника.  8.5. Виконавець і Замовник гарантують власнику немайнових прав на твір архітектури безперешкодний доступ до всіх видів робіт у будь-який час протягом всього періоду виконання робіт за умови дотримання правил поведінки, окремих вимог пропускного та внутрішнього об’єктного режиму, пожежної безпеки, охорони праці, ввезення та вивезення матеріальних цінностей, іншого майна, відходів тощо, порядку виконання робіт.  8.6. Авторський нагляд здійснюється з урахуванням вимог постанови Кабінету Міністрів України від 11 липня 2007 року № 903 «Про авторський та технічний нагляд під час будівництва об'єкта архітектури»  **9. Нагляд і контроль**  9.1. Нагляд та контроль здійснюється Замовником та Інженером, на умовах та згідно з правами та обов’язками, визначеними контрактом між Інженером та Замовником.  9.2. Для контактів з Виконавцем з питань, пов’язаних з виконанням предмету даного Договору, Замовник наказом Держмитслужби призначає уповноважену особу та представників.  9.3. Виконавець призначає:  9.3.1. Керівника будівництва: інженер-будівельник протягом 5 днів з дати затвердження проєкту будівництва (реконструкції);  9.3.2. Інспектором з охорони праці: протягом 5 днів з дати затвердження проєкту будівництва (реконструкції).  9.3.3. Виконавець уповноважує їх представляти себе по питаннях, пов’язаних з виконанням предмету даного Договору, про що Виконавець повідомляє Замовника листом протягом 3 днів з дати призначення.  9.4. Існує можливість заміни осіб, вказаних у п. 9.2 і п. 9.З даного Договору, шляхом оформлення письмового повідомлення сторонами одна одну. Замовник може вимагати від Виконавця замінити осіб, вказаних у п. 9.3 даного Договору, у випадку виявлення неналежного виконання ними своїх обов’язків за договором. Виконавець зобов’язаний замінити цих осіб у строк, вказаний у вимозі Замовника.  **10. Прийняття предмету замовлення**  10.1. Сторони передбачають прийняття виконання проєктних робіт, підготовчих робіт та будівельних робіт з урахуванням матеріалів і обладнання окремими документами у відповідності до положень розділу 10 даного Договору.  10.2. Сторони постановили, що про прийняття, передбачені у пункті 10.1 цього Договору, мають складатися відповідні акти, які повинні містити усі деталі процесу прийняття, а також терміни усунення виявлених дефектів і недоліків.  10.3. Прийняття проєктних робіт відбувається проведенням кінцевого прийняття проєктних робіт за договором з оформленням документів, вказаних у пункті 11.3.1. Договору та включає в себе 100% вартості проєктних робіт, виконаних в рамках цього Договору. Відбувається після передання Замовнику повного комплекту робочої документації на всі етапи підготовчих і будівельних робіт з оформленням актів здачі-приймання документації (Додаток 12) або проєктної документації щодо коригування затвердженого проєкту разом з висновком експертизи з оформленням Акт прийому-передачі технічної документації (Додаток 12).  10.4. Прийняття підготовчих робіт відбувається проведенням кінцевого прийняття підготовчих робіт після виконання Виконавцем 100% обсягу цих робіт у відповідності з затвердженими Замовником та погодженими Виконавцем Проектом організації будівництва та Проектом виконання робіт з оформленням документів, вказаних в пункті 11.3.4 даного Договору.  10.5. Прийняття будівельних робіт і пусконалагоджувальних робіт відбувається проведенням щомісячного та кінцевого прийняття робіт за Договором.  10.5.1. Щомісячне прийняття виконаних будівельних робіт і пусконалагоджувальних робіт відбувається з оформленням документів, вказаних в пункті 11.3.3 даного Договору;  10.5.2. Кінцеве прийняття предмету за Договором Замовником відбувається після виконання Виконавцем усього обсягу робіт, що є предметом цього Договору, отримання спільно із Замовником дозволу на експлуатацію, завершення робіт з упорядкування, закінчення та дотримання усіх формальних вимог, передбачених цим Договором та законодавством України, підписання Акту здачі-приймання робіт (Додаток 10) та передання Замовнику повного комплекту виконавчої документації, з оформленням документів, вказаних в пункті 11.3.4 даного Договору та Акту прийому-передачі технічної документації (Додаток 12).  10.6. Прийняття, про які йдеться у пунктах 10.4 та 10.5 Договору, вважаються проведеними за умови підписання актів (Додатки 7, 10 і 16) Замовником без застережень.  10.7. Акти (Додатки 7, 10, 16) підписуються у такій послідовності:  1) «Роботу здав» – Виконавець (керівник будівництва);  2) «Роботи перевірив та погодив» – Інженер;  3) «Роботи прийняв» – Замовник (уповноважений представник).  10.8. Разом з актами (Додатки 10 і 16) надаються документи, що підтверджують якість використаних матеріалів та обладнання, а також відповідні документи, що підтверджують їх походження, наприклад: митні декларації та сертифікати про походження.  10.9. Представник Замовника та Інженер протягом трьох днів після отримання комплекту документів, вказаних в пунктах 11.3.1, 11.3.2 11.3.3 та 11.3.4. перевіряє виконання робіт, згідно представлених документів, після чого уповноважена особа Замовника підписує їх в частині фактично виконаних робіт.  10.10. Виконавець повинен повідомляти Інженера і Замовника про необхідність проведення прийняття робіт, що підлягають завершенню і закриттю, протягом 2 днів з моменту їх виконання шляхом внесення відповідного запису у журнал будівництва та направлення відповідного повідомлення. Інженер повинен провести перевірку виконання робіт, що підлягають завершенню і закриттю, протягом 3 днів з моменту повідомлення. Замовник повинен прийняти роботи протягом 2 днів з моменту погодження їх Інженером.  Неприйняття робіт протягом цього строку не може спричинити зупинку робіт, а роботи, що підлягали завершенню і закриттю, вважаються виконаними у належний спосіб.  10.11. Виконавець повинен у письмовій формі повідомити Замовника про завершення виконання усього комплексу робіт та готовність до прийняття за 5 робочих днів до запланованого кінцевого прийняття, одночасно вносячи відповідний запис у журнал будівництва.  10.12. Умовою скерування Виконавцем повідомлення про свою готовність до проведення кінцевого прийняття є завершення виконання усього комплексу робіт, отримання Виконавцем передбачених чинним законодавством свідоцтва і дозволів на системи, встановлені або споруджені у процесі виконання предмету даного Договору, а також дотримання формальних вимог, передбачених даним Договором та законодавством України та отримання дозвільного документу на експлуатацію об’єкту.  10.13. У випадку виявлення у процесі прийняття, що предмет Договору не готовий до прийняття з огляду на незакінчені роботи, неотримання Виконавцем відповідних дозволів або викриття дефектів, що унеможливлюють експлуатацію, кінцеве прийняття має бути призупинене до моменту усунення Виконавцем усіх недоліків. Після усунення виявлених недоліків Виконавець зобов’язаний повторно повідомити Інженера і Замовника про готовність предмету Договору до прийняття у порядку, передбаченому у п.10.12 даного Договору.  10.14. У випадку виявлення дефектів і недоліків, які не обмежують експлуатацію, обидві Сторони повинні узгодити термін їхнього усунення, що не перевищуватиме 14 днів з моменту прийняття. Виконавець зобов’язаний повідомити Інженера і представника Замовника про усунення дефектів і недоліків, вказаних в акті, та отримати від Замовника письмове підтвердження того, що дефекти і недоліки були усунені належним чином.  10.15. Перед початком процедури кінцевого прийняття Виконавець повинен надати Замовнику всю виконавчу документацію за об’єктом будівництва, відповідність і повноту якої підтверджено Інженером.  10.16. У разі відмови однієї із сторін від підписання актів, сторони діють в порядку передбаченому пунктом 4 статті 882 Цивільного кодексу України.  **11. Умови здійснення розрахунків**  11.1. Платежі сплачуються Урядом Республіки Польща, через банківську установу, уповноважену обслуговувати Кредит – Bank Gospodarstwa Krajowego (далі – Банк), відповідно до частини 1 статті 10 Договору між Урядом України та Урядом Республіки Польща про надання кредиту на умовах пов’язаної допомоги від 09.09.2015, з Державного бюджету Республіки Польща у польських злотих. Усі ціни, встановлені відповідно до світових ринкових цін та ціна Договору, виражаються в EURО.  Оплата здійснюється поетапно по факту прийняття робіт, як це передбачено §10 даного Договору.  11.2 За домовленістю Сторін та погодженням Міністерства фінансів України здійснюється авансовий платіж Замовником для проведення закупівлі товарів робіт і послуг в рамках Договору у розмірі до 60% від загальної вартості Договору (за умови наявності та у розмірі не більше 80% відповідного бюджетного призначення) на строк до повного виконання зобов’язань за Договором, а саме \_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_євро \_\_ центів ), з яких:  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_ євро \_\_ центів ) – вартість робіт, зазначених у пункті 3.1.1 Договору;  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_ євро \_\_ центи) – частина вартості підготовчих, будівельних робіт, зазначених у пунктах 3.1.2 і 3.1.3 Договору.  11.2.1. Документами на оплату авансового платежу, що надаються Виконавцем є:  - Інвойс/рахунок на здійснення авансового платежу (Додаток 14) – 3 оригінали (один примірник залишається у Замовника) + 2 копії;  - Декларація (повідомлення) Виконавця про спосіб використання авансового платежу (Додаток 15) - 3 оригінали (один примірник залишається у Замовника) + 2 копії.  11.2.2. Авансовий платіж (за виключенням вартості робіт, зазначеної в пункті 3.1.1) погашається Виконавцем шляхом утримання коштів із суми, що підлягає до оплати Виконавцю робіт, виконаних за звітний період, і вказується зі знаком мінус в Інвойсі/рахунку за виконані роботи і використані матеріали та встановлене обладнання (Додаток 3) пропорційно до суми, що підлягає оплаті по відношенню до Договірної ціни Договору, вказаної в п. 3.1. Договору.  11.2.3. У разі розірвання Договору до його повного виконання, незалежно від того яка сторона виступає ініціатором такого розірвання, непогашена частина авансового платежу повертається Виконавцем відповідно до абзацу 2 пункту 3 Порядку реалізації Договору між Урядом України та Урядом Республіки Польща про надання кредиту на умовах пов’язаної допомог, затвердженого постановою Кабінету Міністрів України від 14 лютого 2017 р. № 73 або погашається шляхом взаєморозрахунків за виконані роботи 10 днів з моменту розірвання Договору.  11.3. Платежі за виконані роботи, матеріали та обладнання, в тому числі, ввезені на умовах «INCOTERMS 2010 – DAP Шегині» сплачуються на підставі наступних умов та документів.  11.3.1. Відшкодування за виконанні проєктні роботи сплачуються у розмірі 100 відсотків вартості виконаних проєктних робіт на підстві наступних документів:  11.3.1.1 Інвойс/рахунок за виконані роботи (Додаток 6), що підлягає оплаті, підписаний Виконавцем і Замовником – 3 оригінали (один примірник залишається у Замовника) + 2 копії;  11.3.1.2. Акт прийняття виконаних проєктних робіт (робіт з авторського нагляду) (Додаток 7), підписаний Виконавцем і Замовником – по 3 оригінали (по одному примірнику залишається у Замовника) + 2 копії.  11.3.1.3 Завірена Виконавцем копія документу, що підтверджує здійснення оплати проєктних робіт за договором між Виконавцем та проєктувальником - по 3 копії документу (один примірник залишається у Замовника);  11.3.1.4 У разі проведення оплати, визначеної пунктом 11.3 додатково надаються: Акт прийому-передачі технічної документації (Додаток 12).  11.3.2. Відшкодування за виконанні роботи з авторського нагляду сплачуються у розмірі 100 відсотків вартості виконаних робіт з авторського нагляду на підстві наступних документів:  11.3.2.1 Інвойс/рахунок за виконані роботи (Додаток 6), що підлягає оплаті, підписаний Виконавцем і Замовником – 3 оригінали (один примірник залишається у Замовника) + 2 копії;  11.3.2.2. Акт прийняття виконаних проєктних робіт (робіт з авторського нагляду) (Додаток 7) підписаний Виконавцем і Замовником – по 3 оригінали (по одному примірнику залишається у Замовника) + 2 копії.  11.3.2.3 Завірена Виконавцем копія документу, що підтверджує здійснення оплати робіт з авторського нагляду за договором між Виконавцем та власником немайнових прав на твір архітектури - по 3 копії документу (один примірник залишається у Замовника);  11.3.3. Проміжні (щомісячні) платежі за виконання робіт, використані матеріали та встановлене обладнання, сплачуються на підставі наступних документів, оформлених Сторонами відповідним чином:  11.3.3.1. Інвойс/рахунок за виконані роботи і використані матеріали і встановлене обладнання (Додаток 3) на кожну частину виконаних робіт та використаних матеріалів із зазначенням суми, що підлягає до оплати, підписаний Виконавцем і Замовником – 3 оригінали (один примірник залишається у Замовника) + 2 копії;  Сума, зазначена в інвойсі/рахунку за виконані роботи та використані матеріали (Додаток 3) на кожну частину виконаних робіт, визначених пунктом 10.5.1 Договору, не може перевищувати суми 95 відсотків вартості виконаних робіт суми та 100 відсотків вартості використаних матеріалів і встановленого обладнання, зазначеної у акті прийняття виконаних робіт та використаних матеріалів і встановленого обладнання (Додаток 9) та довідці про вартість виконаних робіт та використаних матеріалів і встановленого обладнання (Додаток 8) на кожну частину виконаних будівельних і спеціальних монтажних робіт та використаних матеріалів і встановленого обладнання.  11.3.3.2. Акт здавання-приймання виконаних будівельних робіт (Додаток 16) зі Звітом про виконання робіт за Договором на об’єкті будівництва за період (місяць, рік) (Додаток 9) та Підсумковим звітом про вартість виконаних робіт за Договором на об’єкті будівництва за період (додаток 8) на кожну частину виконаних будівельних і спеціальних монтажних робіт та використаних матеріали і встановленого обладнання за відповідний місяць, підписані Виконавцем і Замовником – по 3 оригінали (по одному примірнику залишається у Замовника) + 2 копії.  11.3.3.3. Примірник мультимодального коносамента або міжнародна товаротранспортна накладна відправника (BL, CMR, AIR WAY BILL) з відміткою Замовника, що підтверджує доставку Товару в пункт пропуску та Пакувальний лист (Додаток 4) - по 3 копії накладної (один примірник залишається у Замовника) + 2 копії пакувального листа (один примірник залишається у Замовника);  11.3.3.4 Протокол прийняття обладнання (Додатком 5), підписаний Виконавцем і Замовником англійською та українською мовами - 3 оригінали (один примірник залишається у Замовника) + 2 копії.  11.3.4. Кінцевий платіж за виконання робіт сплачуються на підставі наступних документів, оформлених Сторонами відповідним чином:  11.3.4.1. Інвойс/рахунок за виконані роботи і використані матеріали та встановлене обладнання (Додаток 3) на кожну частину виконаних робіт із зазначенням суми, що підлягає до оплати, підписаний Виконавцем і Замовником – 3 оригінали (один примірник залишається у Замовника) + 2 копії;  Сума, зазначена в інвойсі/рахунку за виконані роботи та використані матеріали і встановлене обладнання (Додаток 3), визначені пунктом 10.5.2 Договору, повинна становити 5 відсотків вартості, раніше виконаних робіт зазначених у актах прийняття виконаних робіт та використаних матеріалів і встановленого обладнання (Додаток 9) та довідках про вартість виконаних робіт та використаних матеріалів і встановленого обладнання (Додаток 8) на кожну частину виконаних будівельних і спеціальних монтажних робіт та доставлені матеріали та обладнання за весь період будівельних робіт, але не перевищувати різниці між сплаченою сумою та Договірною ціною, визначеною в пункті 3.1 Договору. При цьому документи визначені пунктами 11.3.4.2 – 11.3.4.4 не надаються.  11.3.4.2. Акт здавання-приймання виконаних будівельних робіт (Додаток 16) зі Звітом про виконання робіт за Договором на об’єкті будівництва за період (місяць, рік) (Додаток 9) та Підсумковим звітом про вартість виконаних робіт за Договором на об’єкті будівництва за період (додаток 8) на кожну частину виконаних будівельних і спеціальних монтажних робіт та доставлені матеріали та обладнання за відповідний місяць, підписаний Виконавцем і Замовником – по 3 оригінали (один примірник залишається у Замовника) + 2 копії;  11.3.4.3. Примірник мультимодального коносамента або міжнародна товаротранспортна накладна відправника (BL, CMR, AIR WAY BILL) з відміткою Замовника, що підтверджує доставку Товару в пункт пропуску та Пакувальний лист (Додаток 4) - по 3 копії накладної (один примірник залишається у Замовника) + 2 копії пакувального листа (один примірник залишається у Замовника);  11.3.4.4. Протокол прийняття обладнання (Додатком 5), підписаний Виконавцем і Замовником – 3 оригінали (один примірник залишається у Замовника) + 2 копії.  11.3.4.5. Сплачені Замовником інвойси/рахунки на підтвердження попередньо отриманих коштів – 5 копій (одна залишається у замовника).  11.3.4.6. У разі проведення оплати, визначеної пунктом 10.5.2 Договору додатково надаються: Акт здачі-приймання робіт (Додаток 10), та Акт прийому-передачі технічної документації (Додаток 12), підписані Виконавцем і Замовником - 3 оригінал (один примірник залишається у Замовника) + 2 копії завірені.  11.4. Вказані в пункті 11.3 документи викладаються двома мовами: українською та англійською. В разі будь-яких розбіжностей в тлумаченні переважну силу має текст англійською мовою, крім документів виданих (оформлених) уповноваженими органами України за встановленою законодавством України формою, де переважну силу має текст українською мовою.  11.5. Документи, подані Виконавцем згідно пункту 11.3 (оригінали та копії), повинні бути представлені Виконавцем до реєстру Банку та повинні містити напис «відповідно до Договору між Урядом Республіки Польща та Урядом України про надання кредиту пов'язаної допомоги від 09.09.2015».  11.6. Після отримання документів на оплату Банк повинен передати представлені документи до Міністерства фінансів України, яке передає ці документи Замовнику у дводенний строк. Після отримання від Замовника підтвердження представлених документів Міністерство фінансів України надає повноваження (дозвіл) Банку здійснити оплату Виконавцю. Загальний строк підтвердження представлених документів не може перевищувати 14 днів з дня отримання від Банку.  11.7. Оплата Замовником Виконавцеві – це повноваження (дозвіл) надане Міністерством фінансів України на користь Банка за дорученням Замовника на виплату Виконавцю належної оплати.  11.8. Виконавець, у випадку відсутності оплати за виконані роботи після закінчення терміну визначеного в пункті 11.6 Договору має право призупинити роботи, про що має негайно повідомити Замовника, а у випадку прострочення оплати більш ніж на 45 днів Виконавець має право розірвати Договір або відмовитись від його виконання.  11.9. Замовник та Виконавець не несуть відповідальність за дії або бездіяльність органів виконавчої влади України і Республіки Польща, задіяних в реалізації Договору відповідно до умов Договору між Урядом України та Урядом Республіки Польща про надання кредиту на умовах пов’язаної допомоги від 09.09.2015.  **12. Гарантії**  12.1. Виконавець гарантує комплексне і якісне виконання предмету Договору згідно з вимогами нормативно-технічних документів, державних стандартів України, Технічній специфікації та проєкту, технічними знаннями і будівельною наукою.  12.2. Виконавець надає Замовнику гарантію на предмет замовлення з наступними гарантійними термінами:  12.2.1. скануюче обладнання – 3 роки,  12.2.2. обладнання системи відеоконтролю – 3 роки,  12.2.3. серверне обладнання – 3 роки;  12.2.4. обладнання структурованої кабельної системи – 20 років;  12.2.5. персональні комп’ютери – 3 роки;  12.2.6. дорожнє покриття – 3 роки;  12.2.7. дорожні знаки – 2 роки;  12.2.8. огородження – 3 роки  12.2.9. каркаси будівель та споруд, стіни, покриття та перекриття – 10 років;  При цьому терміни не можуть бути меншими термінів, визначених в «Інформації про необхідні технічні, якісні та кількісні характеристики предмета закупівлі».  12.3. Датою початку гарантійного періоду є дата введення об’єкту в експлуатацію, а якщо при кінцевому прийманні робіт буде виявлено недоліки, датою початку гарантійного строку є дата усунення дефектів і недоліків, вказаних в акті кінцевого здавання-приймання і продовжується на строк, впродовж якого об’єкт, на якому виконані роботи, не міг експлуатуватися внаслідок недоліків, відповідальність за які несе Виконавець.  12.4. Детальні умови гарантії наводяться у гарантійних документах, переданих Виконавцем Замовнику у момент кінцевого прийняття робіт.  12.5. Виконавець відповідає за дефекти, виявлені у межах гарантійного строку, окрім випадків, коли дефекти виникли з причин, незалежних від Виконавця.  **13. Розірвання договору**  13.1. Якщо затримка з початком, виконанням або завершенням окремих частин або предмету Договору в цілому буде настільки тривалою, що ставитиме під сумнів закінчення робіт Виконавцем у строк, вказаний у пункті 2.1 даного Договору, і Виконавець не вжив заходів щодо усунення такого прострочення, Замовник матиме право розірвати договір.  13.2. У випадку неякісного виконання предмету договору з порушенням умов Договору, Замовник може вимагати від Виконавця змінити спосіб роботи у встановлений термін, що розпочнеться з моменту вручення Виконавцю відповідного повідомлення. Якщо спосіб роботи не буде змінений у встановлений спосіб, Замовник може:  13.2.1. розірвати договір;  13.2.2. доручити виправлення недоліків іншому суб'єкту за рахунок і на ризик Виконавця.  13.3. Крім цього, Замовник може розірвати договір у випадку:  13.3.1. подання кредиторами заяви про оголошення Виконавця банкрутом до відповідного суду та оголошення Виконавця банкрутом;  13.3.2. арешту майна Виконавця уповноваженими органами з метою відшкодування, примусового стягнення або іншого розпорядження майном Виконавця задля уникнення неможливості відшкодування претензій кредиторів;  13.3.3. у випадках, передбачених чинним законодавством України.  13.4. Виконавець може розірвати Договір у випадку необґрунтованої відмови Замовника від прийняття робіт, виконаних у рамках даного Договору, і у випадку, якщо затримання з оплатою виконаних робіт триває більше, ніж 45 (сорок п’ять) календарних днів з дня настання обов’язку щодо оплати визначеного в пункті 10.8. Договору.  13.5. У випадку розірвання договору однією зі сторін Виконавець зобов'язаний негайно зупинити роботи і забезпечити охорону незавершених робіт та будівельного майданчика.  13.6. У випадку розірвання договору однією зі сторін протягом 14 днів з моменту вручення заяви про розірвання має бути призначена комісія та здійснена оцінка вартості виконаних робіт станом на день розірвання, а також проведене прийняття-передачі території виконання робіт.  13.7. У разі ухиляння однієї зі сторін від процедури, описаної у попередньому пункті, друга сторона матиме право самостійно здійснити відповідні дії, а прийняті нею рішення вважатимуться дійсними.  13.8. Сторони також можуть розірвати Договір на підставі виникнення умов, зазначених в пункті 3.5 цього Договору.  13.9. У випадку розірвання Договору сторони дотримуються вимог передбачених абзацем 2 пункту 3 Порядку реалізації Договору між Урядом України та Урядом Республіки Польща про надання кредиту на умовах пов’язаної допомог, затвердженого постановою Кабінету Міністрів України від 14 лютого 2017 р. № 73.  **14. Договірні штрафи**  14.1. У разі невиконання або неналежного виконання своїх зобов’язань за даним Договором Сторони несуть відповідальність, передбачену законодавством України та даним Договором.  14.2. Види порушень та санкції за них установлені Договором:  14.2.1. Виконавець несе відповідальність в тому числі за: незабезпечення безпеки на території об’єкту згідно діючих нормативів при виконанні робіт.  14.2.2. Виконавець несе відповідальність за дотримання всіх необхідних правил санітарної та протипожежної безпеки, правил охорони праці, а також за техніку безпеки під час виконання робіт та організацію безпечного проїзду транспорту під час виконання ним робіт.  14.2.3. Сторони звільняються від відповідальності за невиконання умов цього Договору, якщо це невиконання або неналежне виконання є наслідком причин, що знаходяться поза контролем виконавчої Сторони, таких як пожежі, стихійні лиха, воєнні дії, торгове ембарго, протиправні дії третіх осіб (далі «форс-мажорні обставини»). У цьому випадку виконання умов цього Договору відкладається на термін, протягом якого будуть діяти такі умови.  14.2.4. Виконавець також несе відповідальність за порушення з його вини строків виконання робіт, визначених у п. 2.1 даного Договору шляхом сплати пені у розмірі облікової ставки НБУ, що діє в період, на який нараховується пеня від суми невиконаного або неналежним чином виконаного зобов’язання за період прострочення.  14.2.5. За несвоєчасне або неналежне виконання Сторонами інших своїх зобов’язань за Договором винна Сторона сплачує пеню в розмірі подвійної облікової ставки НБУ річних, що діє в період на який нараховується пеня, від суми невиконаного або неналежним чином виконаного зобов’язання за період прострочення.  14.2.6. Сплата за відшкодування збитків не звільняє винну у порушенні договірних зобов'язань Сторону від їх виконання у повному обсязі.  14.3. Виконавець несе матеріальну відповідальність за збереження виконаних робіт, наслідки їх пошкодження або знищення до моменту прийняття робіт Замовником. 3 моменту підписання цього Договору Виконавець несе матеріальну відповідальність за збереження переданих йому на утримання складових елементів об’єкту. У разі випадкового пошкодження переданих йому на утримання складових елементів об’єкту до передачі його Замовнику Виконавець зобов'язаний терміново повідомити про це Замовника та негайно власними силами усунути пошкодження, якщо така шкода завдана з вини Виконавця через його дії чи бездіяльність. На вимогу Замовника Виконавець подає йому для погодження план заходів щодо усунення випадкового пошкодження об'єкта. За погодженням із Замовником Виконавець може залучати до усунення пошкодження об'єкта третіх осіб за власний рахунок.  14.4. Виконавець зобов'язаний вжити заходів для запобігання знищенню або пошкодженню об'єкта. У разі необхідності Сторони вносять відповідні зміни в умови Договору в зв'язку з появою цих обставин.  14.5. Виконавець несе відповідальність за дотримання вимог нормативно-правових документів на період з початку проведення робіт і до їх здачі Замовнику.  14.6. У випадках, непередбачених цим Договором, Сторони несуть відповідальність передбачену чинним законодавством України.  **15. Форс-мажор**  15.1. Обставинами непереборної сили вважаються події (зокрема, війна, терористичні акти, катастрофи, стихійні лиха, заворушення, страйки, пожежі, несприятливі атмосферні умови), на які сторони не мають впливу і які повністю або частково ускладнюють або унеможливлюють виконання робіт, суттєво змінюють умови виконання робіт та не піддаються уникненню, незважаючи на вжиття усіх можливих заходів.  15.2. Сторона, яка посилається на форс-мажорні обставини, повинна підтвердити факт їхнього виникнення в порядку, установленому законодавством України чи Польщі відповідно.  **16. Технічний нагляд за проєктуванням**  **та виконанням робіт**  16.1. Технічний нагляд за проєктуванням та виконанням робіт здійснюється підприємством (організацією), яка здійснюватиме консультаційні послуги щодо супроводження проєкту будівництва (надалі – Інженер), визначеним за результатами відкритих торгів, проведених ДФС (правопопередник Держмитслужби), на умовах, правах та обов’язках відповідно до Контракту між Інженером та Держмитслужбою (надалі – іменується Контракт).  16.2. Основною метою та завданням для Інженера є сприяння Замовнику в управлінні Договором, який фінансується Урядом Республіки Польща, з належною старанністю та виконання зобов’язань Інженера, обумовлених в Контракті. Інженер повинен виконувати повноваження властиві Інженеру, як зазначено в Контракті або неминуче випливають з нього, для забезпечення своєчасного, задовільного завершення робіт згідно з Договором.  16.3. Надання послуг Інженером поділяється на два етапи: надання послуг під час проєктування і надання послуг під час виконання будівельних робіт.  16.4. Обов’язки Інженера включають наступні завдання:  16.4.1. сприяння Замовнику в контролі за ходом виконання проєктних робіт;  16.4.2. сприяння Замовнику в аналізі проєктних рішень, розроблених Виконавцем, на відповідність чинних в Україні норм і стандартів;  16.4.3. інспектування робіт для перевірки їх відповідності специфікаціям та кресленням;  16.4.4. перевірка і затвердження лабораторій Виконавця для виконання контрольних випробувань матеріалів та виконаних робіт, видача розпоряджень про усунення неналежних робіт або таких, що не відповідають стандартам, згідно з діючими в Україні технічними правилами щодо нагляду за роботами;  16.4.5. контроль матеріалів, що використовуються в роботах (включаючи перевірочні випробування в лабораторії Інженера);  16.4.6. реєстрація щоденних подій на робочому майданчику і обсягів робіт для оплати (за результатами геометричних вимірів та перевірки якості);  16.4.7. у разі затримки ходу виконання робіт у порівнянні з початковою або оновленою та затвердженою програмою робіт та якщо передбачається відкладення передбаченої Договором дати завершення робіт, вжиття всіх необхідних заходів для прискорення робіт і повідомлення Замовника в установленому порядку;  16.4.8. у разі відкладення передбаченої Договором дати завершення робіт визначення причин та оцінка наслідків для Договору, звітування Замовнику про наслідки такого відкладення;  16.4.9. встановлення змісту та формату щомісячних звітів, які подає Виконавець Замовнику;  16.4.10. організація умовного, тимчасового і часткового прийняття робіт і передача всіх документів з нагляду приймальній комісії згідно з чинним законодавством;  16.4.11. розрахунок неустойок, у разі необхідності;  16.4.12. аналіз і затвердження плану забезпечення якості, поданого Виконавцем, і перевірка його виконання відповідно до специфікації, зокрема Інженер перевіряє виконання всіх випробувань в лабораторії Виконавця за вказаними типами і частотою. Інженер перевіряє якість таких випробувань, проводячи окремі (незалежні) випробування в лабораторії Інженера для перевірки результатів Виконавця;  16.4.13. аналіз претензій, поданих Виконавцем, і звітування про те, чи подані такі претензії згідно з процедурами врегулювання суперечок;  16.4.14. на додаток до аналізу, консультування Замовника, чітко вказуючи на можливі сценарії. Звіт Інженера Замовнику подається у вигляді спеціального звіту, який розглядає конкретну претензію;  16.4.15. негайне звітування Замовнику про події або спори, які вимагають втручання Замовника, і допомога у вирішенні таких спорів;  16.4.16. нагляд за Виконавцем з усіх питань, що стосуються безпеки і охорони робіт;  16.4.17. нагляд за Виконавцем з усіх питань, що стосуються охорони довкілля;  16.4.18. нагляд, перевірка і виправлення, у разі необхідності, виконавчих креслень Виконавцем.  16.5. Звітність Інженера перед Замовником здійснюється відповідно до умов контракту між Інженером та Держмитслужбою.  **17. Прикінцеві положення**  17.1. Положення Договору між Урядом України та Урядом Республіка Польща про надання кредиту на умовах пов’язаної допомоги мають вищу силу над положеннями внутрішнього законодавства України, які можуть дозволити Уряду України в односторонньому порядку призупинити чи припинити виконання зобов'язань за цим Договором до того часу, як всі зобов'язання за ним будуть виконані.  17.2. Даний Договір погоджується відповідно до такої процедури:  17.2.1. Міністерство фінансів України у письмовій формі інформує Міністерство фінансів Республіки Польща про схвалення даного Договору;  17.2.2. Надалі Міністерство фінансів Республіки Польща надає Міністерству фінансів України своє письмове підтвердження даного Договору;  17.2.3. Даний Договір набере чинності через 15 (п'ятнадцять) днів з дати надсилання письмового підтвердження Міністерства фінансів Республіки Польща Міністерству фінансів України і діє до завершення зобов’язань, але не більше 5 років з дати набрання чинності Договору;  17.2.4. Процедура узгодження для кожної Сторони не може перевищувати 45 (сорок п'ять) днів.  17.3. Договір про закупівлю буде оприлюднений на веб-порталі уповноваженого органу після письмового підтвердження Міністерства фінансів Республіки Польща Міністерству фінансів України.  17.4. Усі претензії, які можуть виникнути під час виконання цього договору, будуть врегульовані поза рамками Договору між Урядом Республіки Польща та Урядом України про надання кредиту на умовах пов'язаної допомоги від 09.09.2015.  17.5. Усі поправки, доповнення та зміни до умов цього Договору та додатків до них підлягають процедурі погодження, як це передбачено Договором між Урядом Республіки Польща та Урядом України про надання кредиту на умовах пов'язаної допомоги від 09.09.2015, крім змін у реквізитах розрахункових рахунків про які сторони повідомляють одна одну листом.  17.6. Усі банківські комісії, а також всі інші можливі збори, які можуть бути пов'язані з будь-якою причиною, пов'язаною з платежами, здійсненими згідно Договором відповідно до Договору між Республікою Польща та Урядом України про надання кредиту на умовах пов'язаної допомоги від 09.09.2015, будуть сплачені кожною Стороною у своїй країні поза рамками Цього Договору.  17.7. Можливі суперечки, що виникають на тлі виконання даного Договору, підлягають вирішенню в Міжнародному комерційному арбітражному суді при торгово-промисловій палаті України у відповідністю з його регламентом. Правом, регулюючим даний договір є матеріальне право України. Місце проведення засідання Арбітражного суду - м. Київ (Україна). Мова арбітражного розгляду - українська.  17.8. При вирішенні питань, не врегульованих даним договором, застосовуються відповідні положення законодавства, що пов'язані з виконанням предмету договору.  17.9. Усі зміни до Договору повинні мати письмову форму, інакше вони вважатимуться недійсними.  17.10. Договір укладений у чотирьох ідентичних примірниках українською та англійською мовами, три з яких передаються Замовнику, один – Виконавцю. У разі виявлення розбіжностей між українською та англійською версіями Договору, українська версія має перевагу.  17.11. Уся, пов’язана з даним Договором, переписка ведеться українською та англійською мовами.  17.12. Сторони домовилися, що уся пов’язана з даним Договором переписка, надіслана за допомогою факсимільного зв’язку або електронною поштою, мають силу оригіналу.  **18 Додатки**  18.1. Додаток 1: Інформація про необхідні технічні, якісні та кількісні характеристики предмета закупівлі;  18.2. Додаток 2: Договірна ціна;  18.3. Додаток 2.1: Договірна ціна на будівництво;  18.4. Додаток 3: Інвойс/рахунок за виконані роботи та використані матеріали і встановлене обладнання;  18.5. Додаток 4: Пакувальний лист до фактури-фактури;  18.6. Додаток 5: Протокол прийняття обладнання;  18.7. Додаток 6: Інвойс/рахунок за виконані Роботи;  18.8. Додаток 7: Акт прийняття виконаних проєктних робіт (робіт з авторського нагляду);  18.9. Додаток 8: Підсумковий звіт про вартість виконаних робіт за Договором на об’єкті будівництва за період;  18.10. Додаток 9: Звіт про виконання робіт за Договором на об’єкті будівництва за період (місяць, рік);  18.11. Додаток 10: Акт здачі приймання робіт;  18.12. Додаток 11: Акт передання будівельного майданчика;  18.13. Додаток 12: Акт прийому-передачі технічної документації;  18.14. Додаток 13: Перелік механізмів, машин та обладнання;  18.15. Додаток 14: Інвойс/рахунок на здійснення авансового платежу;  18.16. Додаток 15: Декларація (повідомлення) Виконавця про спосіб використання авансового платежу.  18.17. Додаток 16: Акт здавання-приймання виконаних будівельних робіт  **19. Юридичні адреси і реквізити сторін** | **AGREEMENT**  for performance of works on design and construction  city of Kyiv "\_\_\_\_"\_\_\_\_\_\_\_\_\_\_\_ 2023  **The State Customs Service of Ukraine** hereinafter referred to as the **Customer**, represented by the Acting Chairman of the State Customs Service of Ukraine Serhii Zviahintsev, acting on the basis of the Regulations on the State Customs Service of Ukraine, approved by the Resolution of the Cabinet of Ministers of Ukraine of March,6 2019, No. 227 and, on the one part,  And\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, hereinafter referred to as the **Contractor**  according to the results of the procurement procedure of "\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_", in accordance with the terms and conditions of the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit dd. 09.09.2015 (the Agreement was ratified by the Law of Ukraine No. 977-VIII dd. 03.02.2016) and the Resolution of the Cabinet of Ministers of Ukraine "Some Issues of Implementation of the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit" dd. 14.02.2017 No. 73 (as amended), according to which the responsible executor under the relevant budget program is the State Customs Service of Ukraine, concluded an Agreement with the following content:  **1. Scope of the Agreement**  1.1. The Contractor undertakes, in the manner and on the terms determined by this Agreement, using their own forces and means specified in the List of mechanisms, machines and equipment (Annex 13), which is the part of this Agreement, at their own risk and/or with the involvement of subcontractors, to perform and hand over the completed works on the Reconstruction of the Sheghini international checkpoint for road traffic on the Ukrainian-Polish border according to the design and construction model within the term specified by this Agreement.  1.2. Title of facility: works **on “Reconstruction of the Sheghini international checkpoint for road traffic on the Ukrainian-Polish border according to the design and construction model.**  1.3. The Customer shall transfer the territory of construction to the Contractor a month before the day of the construction work commencement upon request of the Contractor. The transfer of the construction site should take place on the basis of the Act of acceptance of the construction site (Annex 11). The Customer is obliged to provide the Contractor with access to the object in order to carry out the measurement diagrams of existing infrastructure of the checkpoint and inspection reports of their technical condition by the moment of transfer of the construction site.  1.4. Location address of the place of fulfillment of the order: Sheghini International Checkpoint for Road Traddic, 201 Druzhby str., Yavoriv district, Lviv region.  1.5. The subject scope of work consists of design works and construction works, the scope of which is determined by the project documentation.  1.6. The volume of the construction works may be changed by the Customer in the interests of project fulfillment, including in case if additional works are not considered by the project, but required for commissioning the object or improvement of the order (procurement) item and inseparably linked to the order (procurement) item should be performed. The additional volume of works is fulfilled within the framework of the contract price at the expense of the costs required for covering the risks considered in the contract price after the project correction by introduction of amendments to the Agreement.  **2. Deadline for the work performance**  2.1. The Parties agreed that the subject of the Agreement should be fulfilled within \_\_\_\_\_ (\_\_\_\_\_\_\_\_) calendar months from the date of conclusion of this Agreement in accordance with the procedure of acceptance stipulated by terms of the Agreement between the Government of Ukraine and the Government of the Republic of Poland on the provision of the loan under the terms of tied aid from September 09, 2015 and clause 16.2 of this Additional Agreement, including upon:  2.1.1. Preparatory works within the area of exit from Ukraine (the first launch complex): \_\_\_\_\_\_\_\_ (\_\_\_\_\_\_) months from the moment of receiving the permission for construction work performance and transfer of the construction site;  2.1.2. Reconstruction of the area of exit from Ukraine (the first launch complex): \_\_\_\_\_\_\_\_ (\_\_\_\_\_\_);  2.1.3. Commissioning of the area of exit from Ukraine (the first launch complex): within \_\_\_\_\_\_\_\_ (\_\_\_\_\_\_) months;  2.1.4. Preparatory works within the area of entrance to Ukraine (the second launch complex): \_\_\_\_\_\_\_\_ (\_\_\_\_\_\_) months from the moment of transfer of the construction site;  2.1.5. Reconstruction of the area of entrance to Ukraine (the second launch complex): \_\_\_\_\_\_\_\_ (\_\_\_\_\_\_);  2.1.6. Commissioning of the area of entrance to Ukraine (the second launch complex): within \_\_\_\_\_\_\_\_ (\_\_\_\_\_\_) months.  after the completion of preparatory work;  2.2. The parties agreed that the terms of performance of works (stages of works) shall be extended for the period of impossibility of performance of works (above specified stages of works) for reasons beyond the control of the Contractor such as, but not limited to delay in obtaining permission for the execution of construction works by the Customer, delay in the transfer over the construction site etc. In case of delays in the execution of works (stages of works) for reasons independent of the Contractor, the latter immediately (no more than five working days from the date of occurrence of the relevant circumstances) notifies the Customer about such occurrence. 2.3. The date of completion of the subject of the Agreement is the date of putting the object into operation in accordance with the requirements of the Procedure for accepting completed construction projects into operation, approved by the resolution of the Cabinet of Ministers of Ukraine dated April 13, 2011 No. 461.  **3. Contract price**  3.1. For execution of the subject of the Agreement, the Contractor shall be paid money funds in amount of EURO \_\_\_\_\_\_(\_\_\_\_\_\_\_\_\_), provided that the cost of materials, equipment, works and services of Polish origin may not be less than 60 % (sixty percent) of the value of this Agreement.  For the purpose of this Agreement and in accordance with Article 11 of the Agreement between the Government of Ukraine and Government of the Republic of Poland on extending a tied aid credit, concluded on September 09, 2015 in Warsaw, operations for import of goods into the customs territory of Ukraine and/or delivery of goods/works/services to the customs territory of Ukraine by the Contractor – a resident of the Republic of Poland exclusively for the implementation of this Agreement shall be exempt from taxation of the value added tax in accordance with the national legislation of Ukraine, even if in the custom territory of the Republic of Poland the applicable VAT rate is “0” for the same goods/works/services according to the national legislation of the Republic of Poland.  3.1.1. Compensation of cost of works in terms of issue of working drawings, working documentation, project correction, author supervision, etc.: \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.1.2. Preparatory works within the area of exit from Ukraine (the first launch complex): \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_), including the cost of materials and equipment: \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_) and the cost of works and services: \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.1.3. Reconstruction of the area of exit from Ukraine (the first launch complex): \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_), including the cost of materials and equipment: \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_) and the cost of works and services: \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.1.4. Commissioning of the area of exit from Ukraine (the first launch complex): \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.1.5. Preparatory works within the area of entrance to Ukraine (the second launch complex): \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_), including the cost of materials and equipment: \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_) and the cost of works and services: \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.1.6. Reconstruction of the area of entrance to Ukraine (the second launch complex): \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_), including the cost of materials and equipment: \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_) and the cost of works and services: \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.1.7. Commissioning of the area of entrance to Ukraine (the second launch complex): \_\_\_\_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_).  3.2. The Contractor shall perform the works using their own materials, means and equipment, the cost of which is determined by the Contract Price in EUR (Annex 2) including the Contract price for construction (Annex 2.1). The Contract Price is fixed.  At the same time, the Contractor may import the required materials and equipment to the customs territory of Ukraine via their permanent representative office for the purposes of performing works under this Agreement and perform their customs clearance directly at the place of work performance, which is Sheghini International Checkpoint of Lviv customs.  All the export documents, first of all invoices, shall include the provision “by Agreement between Government of Ukraine and Government of the republic of Poland on extending a tied aid credit dd 09.09.2015”.  3.3. Source of financing 100% of the loan funds received under the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit dd. 09.09.2015 (hereinafter referred to as the Loan).  Any taxes, fees, and other payments that may arise in relation to the implementation of this Agreement shall be paid by each party to the Agreement in its respective country and shall not be funded by the Loan. Goods, works and services financed under this Agreement are exempted from payment of any taxes, duties or other charges or obligatory payments set out by Ukraine or in its territory in accordance with the current legislation of Ukraine.  3.4. The payment referred to in the preceding clause shall cover the complete implementation of the subject of this Agreement specified in the Section 1, as well as all works and actions having effect on passing the expertise of the working project, obtaining the work permit and the permit for operation, as well as other documents required for the final acceptance of the subject of the Agreement.  The payment referred to in clause 3.1 hereof shall remain unchanged until the completion of the subject of the Agreement.  3.5. The price of the Agreement may be changed, including upward, taking into account changes in market prices for goods in the countries of the Parties during the period of execution of the Agreement. Changes in the value of the Agreement are carried out exclusively in the part of unfinished and additional works in the presence of a positive expert report based on the results of the adjustment of the project documentation, issued in accordance with the procedure established by Ukrainian legislation. Amendments to the Agreement are agreed by the Contracting Parties in accordance with Clause 4 of Article 3 of the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit dd. 09.09.2015.  **4. Subcontract**  4.1. By agreement with the Customer, the Contractor may engage another entity (Subcontractor) for the work performance.  At the same time, the Contractor, when choosing a subcontractor, must take into account the following rules:  - Law of Ukraine “On Sanctions” dated August 14, 2014 No. 1644-VII, and other regulatory and legal deeds adopted based on such Law;  - resolution of the Cabinet of Ministers of Ukraine "On Ensuring the Protection of National Interests in Future Claims of the State of Ukraine in Connection with the Military Aggression of the Russian Federation" dated March 3, 2022 No. 187, since the customer cannot fulfill obligations, the creditors of which are the Russian Federation or persons associated with the country of the aggressor, determined by paragraph 1 of paragraph 1 of the said Resolution;  - resolution of the Cabinet of Ministers of Ukraine "On the application of a ban on the import of goods from the Russian Federation" dated April 9, 2022 No. 426;  - Law of Ukraine "On Ensuring the Rights and Freedoms of Citizens and the Legal Regime in the Temporarily Occupied Territory of Ukraine" dated April 15, 2014 No. 1207-VII.  4.2. The Customer has the right to refuse the Contractor to engage the particular Subcontractor if such Subcontractor does not meet the requirements set forth in clause 4.1.  4.3. The Contractor has the right to engage the economic entities which are residents of Ukraine for performance of works in the amounts not exceeding 40% of the price of the present Contract).  4.4. The Contractor may, if necessary, involve business entities – non-residents of Ukraine to perform the construction works.  4.5. The Contractor shall be responsible for actions or omission of the Subcontractor, the Subcontractor’s representatives or employees, as for own actions or omission.  4.6. An agreement between the Contractor and the Subcontractor may not conflict with the provisions of this Agreement.  4.7. The term of work performance by the Subcontractor shall correspond to the term of execution of the subject of the Agreement concluded between the Customer and the Contractor, as well as to the schedule of works stipulated by the technological process and the principles of building science, which are the subject of the Agreement between the Customer and the Contractor.  4.8. The subcontractor agreement may not contain the provisions that stipulate the dependence between receipt of payment by the subcontractor from the Contractor and receipt of payment by the Contractor for the scope of works performed by the subcontractor.  4.9. The Contractor shall be obliged to present the Subcontractor’s candidacy to the Customer, along with indication of the subject of the subcontractor agreement, details of the Subcontractor, responsible persons provided for hereby no later than 14 days prior to the scheduled date for conclusion of the subcontractor agreement.  4.10. The date of presenting the Subcontractor's candidacy to the Customer shall be the date of submitting the official letter of the Contractor to the Customer's administrative officer at its official email address: post@customs.gov.ua.  4.11. The Customer shall provide written approval of the Subcontractor's candidacy, or written objection with the substantiated explanation within 14 days after receipt of the official letter presenting the Subcontractor's candidacy.  4.12. The Subcontractor's candidacy shall be deemed to be approved upon receipt of written consent from the Customer.  In case of the absence of such an agreement or objection after expiration of the term specified in clause 4.11. of the Agreement, the Subcontractor's candidacy is deemed to be agreed.  4.13. The assignment may be entrusted to another subcontractor than that approved by agreement with the Customer as defined in clause 4.9. Agreement.  **5. Terms of work performance**  5.1. The Contractor represents that they have read the terms of execution of the subject of this Agreement and have taken them into account when determining the contract price hereunder and the term of execution of the subject of this Agreement.  5.2. The Contractor represents that they have read the conditions that should be taken into account during, performance and acceptance of the works. The Contractor represents that in case of detection of mistakes or inconsistencies while designing or performing the works caused by them, they will eliminate them on their own without changing the amount of the contract price and terms of completion considered by this Agreement. All the changes in the scope of construction work different from the project documentation approved by the Customer, as well as all additional works that will arise not from the Contactor's fault, shall be fulfilled by the Contractor only after coordination of their performance period and cost according to the results of correction and expertise of cost of such works, at the expense of cost of risks considered in the Contract Price calculation.  5.3. The Contractor shall fulfill the subject of the Contract according to the project documentation, construction science, current legislation of Ukraine and other valid regulatory documents of Ukraine related to the subject of the Contract..  5.4. The Contractor shall perform/order the development of the work documentation and project correction if required and compensate the author supervision performance to the owner of the non-proprietary rights of the work of architecture within the framework of the cost of such works considered by the approved construction project. The cost of the mentioned works is included into the Contract Price in accordance with Section 3 of the Contract.  5.5. The Contractor guarantees that they are going to transfer the full set of work documentation in paper form in 2 (two) samples and in electronic form in 1 (one) sample, including all the drawings in the DWG format and text documents in the PDF and DOC formats, issued in accordance with the current legislation of Ukraine and considering the available and approved construction project, before the beginning of preparatory and construction works to the Customer.  5.6. The Contractor shall perform the works in accordance with the volume of the order and considering the changed works coordinated with the Customer, if there might be any in accordance with clause 1.6. of this Agreement.  5.7. The Contractor undertakes to execute the subject matter of the Agreement from its own materials (or the subcontractor's materials). The materials used to execute the subject matter of this Agreement must have the appropriate certificates, allowances and permits provided for by the current legislation, comply with the technical specifications for design, performance and acceptance of the works. All goods exported from the Republic of Poland to Ukraine under the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit may not be re-exported to third countries without the written permission of the Minister of Finance of the Republic of Poland. The cost of goods, works and services of Polish origin under the Agreement, financed under the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit dd 09.09.2015, may not be less than 60% (sixty percent) of the cost of this Agreement. The Government of the Republic of Poland may require from the Contractor to provide the detailed information on fulfilment of this requirement, including the provision of the relevant documents, for example, certificates of origin.  5.8. In the course of execution of the subject matter of the Agreement, the Contractor is obliged to observe the rules of safety, industrial sanitation and fire protection.  5.9. The Contractor is considered responsible for the site of performance of the construction works from the moment of its acceptance from the Customer until the time of execution and commissioning the subject of the Agreement and bears the responsibility for possible losses arising from the fault of the Contractor.  5.10. The Contractor is obliged to ensure the protection of the territory of the works performance, including all materials and devices that are located there.  5.11. All construction waste, such as garbage, dismantled materials and devices, should be taken out of the construction site and disposed of. The construction waste should be taken out in the current mode. Waste storage at the works performance site is prohibited.  5.12. In accordance with its needs, the Customer has the right to convene coordination meetings, notifying the Contractor thereon in the current mode; in turn the Contractor is obliged to participate in them.  5.13. Upon completion of the works, the Contractor is obliged to bring the territory occupied by it during the construction works performance (permanently or temporarily) to the starting state, in particular, to restore and clean roads, sidewalks, greenery, etc.  5.14. Aspects and issues not regulated in the specified rules for the performance of work, are subject to approval in the current mode at the stage of construction works performance.  **6. Obligations of the Customer**  6.1. The Customer undertakes to:  6.1.1. Submit design and estimate documentation in accordance with the Act of transfer and acceptance of technical documentation (Annex 12).  6.1.2. Transfer to the Contractor the site for the works performance and to draw up an appropriate certificate under clause 1.3 hereof.  6.1.3. Not prevent the Contractor from the access to the place of contractual work performance;  6.1.4. Specify the points of connection to the power supply and water supply grids.  6.1.6. Accept the works on the terms stipulated by this Agreement and legislation of Ukraine.  6.2. If the Customer detects violations of the terms of the Agreement regarding quality, cost, scopes and terms of performance of the works, including material resources, the Customer shall informs the Contractor of such violations by sending to its e-mail address of the appropriate prescription, that is obligatory for consideration within five (5) working days, and in case if the Contractor fails to provide objections within two (2) calendar days from the date of receipt thereof to e-mail address, it is considered accepted, and the defects specified in the prescription shall be eliminated within fourteen (14) calendar days from the day of receipt of the prescription, and the Contractor shall notify the Customer thereon by a message to the e-mail address.  **7. Obligations of the Contractor**  7.1. The Contractor undertakes to:  7.1.1. Accept the site for the works performance;  7.1.2. Maintain order at the site of the works performance, in particular:  7.1.2.1. ensuring the protection of the site of construction and the property;  7.1.2.2. ensuring the fire protection;  7.1.2.3. supervision over the safety and industrial sanitation;  7.1.2.4. prevention of transport obstacles at the site of the works performance, elimination of accidents related to the construction.  7.1.2.5. designation and marking the site, establishment of a temporary fence.  7.1.3. The Contractor shall bear responsibility to third parties for all losses incurred in relation to the work performance.  7.1.4. Ensure proper organization and coordination of the works by providing appropriate guidance.  7.1.6. Check in detail the conditions at the place of performance of the order.  7.1.7. Provide within a term of no more than 20 working days and agree with the Customer a staged schedule of construction works after approval of the construction design by the Customer. If the Contractor violates the terms set forth in Section 2 of the Agreement through their fault and does not make such overdoes to ensure proper and full compliance with the subject matter of the Agreement, which will result in a violation of the term of completion of works, such breach of the Agreement shall be recognized by the Parties as non-fulfillment of the essential condition of the Agreement and shall be the basis for termination of the Agreement by the Customer unilaterally.  7.1.8. Together with the Customer to obtain a permit for construction works performance in the State Architectural and Construction, for the construction and the construction works performance in a part relevant to the subject of this Agreement.  7.1.9. Start the works performance within the term specified in the schedule of the works performance and notifies the Customer thereon in writing by sending an appropriate message to the Customer's e-mail address and by mail.  7.1.10. Send to the Customer's e-mail address a report on the work performed within 14 calendar days, namely: scopes and types of the works performed, twice, during the current month - on 15th and 30th day, and in the case of days off - on the next working day, no later than 6:00 pm.  7.1.11. Organize the construction site, in particular, to ensure transport, fencing, supply networks, temporary facilities and committing all other actions required for the proper works performance. The Contractor is obliged to ensure the protection and marking of the works in progress and to take care of the technical condition and correctness of the marking during the entire time of construction works performance, to ensure the continuity and safety of passage through the checkpoint, at the sidewalks and parking spaces located around the construction area that are used or crossed through by the Contractor in the course of the works performance, as well as to obtain all necessary approvals and permissions.  7.1.12. Perform and complete construction works in accordance with provisions of the current legislation of Ukraine, safety and industrial sanitation rules.  7.1.13. Collaborate with the services of the Customer and the enterprise (entity) that will carry out advisory services in support of the construction project Engineer on the conditions in accordance clause 15.1. of this Agreement (hereinafter referred to as "the Engineer").  7.1.14. Keep a log of the construction works performance.  7.1.15. Provide personnel and control over the availability of appropriate powers.  7.1.16. Ensure the availability of equipment conforming to the technical standards.  7.1.17. Provide the Customer and Engineer with certificates, permits and technical permissions for used materials, warranty coupons on installed devices and fittings no later than on the day of final acceptance of the works.  7.1.18. Notify the Customer and Engineer in writing of the planned acceptance of the works.  7.1.19. To remove the construction site and transfer the site to the Customer within 14 working days from the date of signing by the parties of the Certificate of final acceptance of the works.  7.1.20. The Contractor shall pay all expenses related to the performance of the duties assigned to it.  7.1.21. In accordance with the rules concerning dangerous substances, the Contractor undertakes to eliminate all dangerous goods delivered to the works performance site, along with tar or packaging. The expenses for removing these substances, along with tar or packaging, shall be borne by the Contractor.  7.1.22. Create an electronic account of a construction participant on the portal of the Unified State Electronic System in the field of construction with the aim of:  1) creation, uploading and signing of documents;  2) entering information about concluded subcontracts, information about the responsible executor of works, who is fixed by the contractor for the relevant construction object;  3) confirmation of involvement in the performance of works (services) related to the creation of architectural objects;  4) confirmation of information about documents created before the introduction of the electronic system;  5) correspondence with users of the electronic system, the holder and the technical administrator;  6) creation and signing of the decommissioning act.  7.2. The Contractor is prohibited from:  7.2.1. Storing directly on the ground waste generated as a result of the works performed, as well as concrete and solutions.  7.2.2. Bring to the Customer's site any waste.  7.2.3. Storing substances that may contaminate water, soil, air, whereas in the case of the use of these substances for the work performance, the details of their storage and use must be agreed with the persons responsible for environmental protection.  7.2.4. Washing the vehicles and equipment at the work performance site.  7.2.5. Burning waste.  **8. Designing and author supervision**  8.1. The development of the work documentation shall be performed upon the order from the Contractor; the correction of the project documentation and author supervision of the construction and assembly works shall be performed by the owner of the non-proprietary rights for the work of architecture, who is the developer of the approved project or persons authorized by them.  8.2. The Contractor shall order the development of the work documentation, the project correction if required and the performance of author supervision within the framework of the cost of such works considered by the approved construction project.  8.3. The Contractor shall include all the provisions of this Agreement, including the corresponding guarantees and requirements, into the Agreement regarding the development of work documentation and project correction.  8.4. All the changes to the approved construction project shall be introduced with the knowledge and consent of the Customer.  8.5. The Contractor and the Customer guarantee the unlimited access to all types of works at any moment within the whole period of work performance to the owner of the non-proprietary rights for the work of architecture upon condition of observation of rules of conduct, certain requirements of pass-entry and internal object regime, fire safety, occupational safety, import and export of material values and other property, waste, etc. and procedure of work performance.  8.6. The author supervision shall be performed considering the requirements of the Resolution of the Cabinet of Ministers of Ukraine dd. July 11, 2007 No. 903 On Author and Technical Supervision during the Construction of an Architectural Object.  **9. Supervision and control**  9.1. Supervision and control shall be carried out by the Customer and the Engineer with the rights and obligations specified in the contract between the Engineer and the Customer.  9.2. For contacts with the Contractor on the issues related to the execution of the subject matter of this Agreement, the Customer, by order of the State Customs Service, shall appoint an authorized person and representatives.  9.3. The Contractor appoints:  9.3.1. Construction manager: engineer-builder within 5 days from approval day of construction project (reconstruction);  9.3.2. Labour safety Inspector: within 5 days from approval day of construction project (reconstruction).  9.3.3. The Contractor authorizes them to represent it on the issues related to the execution of the subject matter of this Agreement, about which the Contractor informs the Customer by letter within 3 days from the date of appointment.  9.4. There is the possibility of replacing the persons specified in clauses 9.2 and 9.3 and of this Agreement, by execution of a written notice by the parties to each other. The Customer may demand from the Contractor to replace the persons indicated in clause 9.3 of this Agreement in case of detecting their improper performance of their obligations under the contract. The Contractor is obliged to replace these persons within the term specified in the Customer's request.  **10. Acceptance of the subject of the order**  10.1. The Parties shall make a provision for fulfillment of design works, preparatory work and construction works taking into account materials and equipment, in separate documents in accordance with provisions of Section 10 of this Agreement.  10.2. The Parties have established that relevant acts shall be executed in relation to acceptance specified in clause 10.1 of this Agreement, that shall include all details of acceptance process and terms of defects and deficiencies discovered elimination.  10.3. Acceptance of project works shall be performed by final acceptance of project works under with the preparation of documents specified in clause 11.3.1 of the Agreement and includes 100% of the total cost of project works performed within the framework of this Agreement. It occurs after the transfer of the complete set of work documentation regarding all the stages of preparatory and construction works with issuance of acts of handing over and acceptance of the documentation (Annex 12) or project documentation regarding correction of the approved project together with the conclusion of the expertise with issuance of Act of transfer and acceptance of technical documentation (Annex 12).  10.4. Acceptance of preparatory works is carried out by the final acceptance of preparatory works after the executes 100% of these works by the Contractor in accordance with Project of Construction Organization approved by the Customer and agreed by the Contractor and the Project of Works Performance, and after transfer of a full set of design with execution of documents specified in clause 11.3.4 of this Agreement.  10.5. Acceptance of construction works and Start-up and adjustment works shall be performed by monthly and final acceptance of works under this Agreement.  10.5.1. Monthly acceptance of construction works Start-up and adjustment works performed shall be conducted with execution of documents specified in clause 11.3.3 of this Agreement;  10.5.2. The final acceptance of the subject under the Agreement by the Customer shall take place after the Contractor performs all scope of works that is the subject of this Agreement, obtaining a permit for operation together with the Customer, performing work on the ordering, completion and observance of all formal requirements provide for hereby and by the legislation of Ukraine signing of the Act of Delivery and Acceptance of the Performed Works (Annex 10) and transfer of a full set of executive documents to the Customer with execution of documents specified in clause 11.3.4 of this Agreement and Act of transfer and acceptance of technical documentation (Annex 12).  10.6. Acceptances specified in clauses 10.4 and 10.5 of the Agreement shall be deemed as completed on condition of acts (Annexes 7, 10 and 16) by the Customer without reservations.  10.7. Acts (Annexes 7, 10 and16) shall be signed in the following sequence:  1) "The work was handed over" - Contractor (Construction Manager);  2) "The works are checked and approved" - Engineer;  3) "The works are accepted" - Customer (Authorized Representative).  10.8. Together with the Act (Annexes 10 and 16), documents confirming the cost of used materials and equipment, as well as relevant documents confirming their origin, such as certificates of origin, shall be provided.  10.9. The Customer’s representative and the Engineer shall check works performance within three days after receipt of set of documents specified in clauses 11.3.1, 11.3.2, 11.3.3 and 11.3.4, thereafter the authorized representative of the Customer shall sign the documents in the part of actually performed works.  10.10. The Contractor must notify the Engineer and the Customer of the need for acceptance of the works to be completed and closed, within 2 days from the date of their performance by entering the relevant record into the construction log and sending the relevant message. The Engineer must carry out an inspection of performance of the works to be completed and closed within 3 days from the date of notification. The Customer must accept the works within 2 days from their approval by the Engineer.  Failure to accept the works within this period cannot cause the works to stop, and the works to be completed and closed are considered to be performed in the proper manner.  10.11. The Contractor must notify the Customer in writing of completing the entire set of works and of the readiness for acceptance 5 working days prior to the scheduled final acceptance, while simultaneously entering the relevant record into the construction log.  10.12. The completion of performance of the entire set of works, obtaining by the Contractor the certificates and permits provided for by the current legislation for the systems installed or constructed in the course of execution of the subject matter of this Agreement, as well as compliance with the formal requirements provided by this Agreement and legislation of Ukraine and obtaining a permit for operation of the facility is the condition for the sending of the notice by the Contractor of its readiness for the final acceptance.  10.13. In case if it is revealed during the process of acceptance that the subject of the Agreement is not ready for acceptance in view of uncompleted works, failure by the Contractor to obtain appropriate permits or detection of defects that make it impossible to operate, the final acceptance shall be suspended until the Contractor has eliminated all deficiencies. After eliminating the deficiencies detected, the Contractor is obliged to re-notify the Engineer and the Customer of the readiness of the subject matter of this Agreement for acceptance in accordance with the procedure provided for in clause 10.12 hereof Agreement.  10.14. In case of detection of defects and deficiencies that do not restrict operation, both parties must agree on the period for their elimination that would not exceed 14 days from the date of acceptance. The Contractor is obliged to notify the Engineer and the Customer's representative of the elimination of defects and deficiencies specified in the certificate and to obtain from the Customer a written confirmation that the defects and deficiencies have been properly eliminated.  10.15. Before commencing the final acceptance procedure, the Contractor must provide the Customer with all executive documentation for the construction facility, the compliance and completeness of which was confirmed by the Engineer.  10.16. In case of refusal of one of the parties from the signing of acts, the parties act in accordance with the procedure provided for in Article 882 paragraph 4 of the Civil Code of Ukraine.  **11. Terms of payments**  11.1. Payments shall be made by the Government of the Republic of Poland through the bank institution authorized to service the Loan - Bank Gospodarstwa Krajowego (hereinafter referred to as the "Bank"), in accordance with Article 10 (1) of the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit dd. 09.09.2015, from the State Budget of the Republic of Poland in Polish zloty. All prices, established in accordance with global market prices and the price of the Agreement are expressed in EURO.  Payment shall be made on a phased basis upon acceptance of works as provided for by Section 10 of this Agreement.  11.2 According to the agreement of the Parties and the approval of the Ministry of Finance of Ukraine, an advance payment is made by the Customer for the purchase of goods, works and services within the framework of the Agreement in the amount of up to 60% of the total value of the Agreement (subject to availability and in the amount of no more than 80% of the corresponding budget allocation) for a period of full fulfillment of obligations under the Agreement, namely \_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_ euros \_\_ cents), of which:  \_\_\_\_\_\_\_\_\_ EURO ( \_\_\_\_\_\_\_\_\_ euros \_\_ cents) – the cost of project works specified in clause 3.1.1 of the Agreement;  \_\_\_\_\_\_\_\_\_ EURO (\_\_\_\_\_\_\_\_\_ euros \_\_ cents) - part of the cost of preparatory and construction works specified in clauses 3.1.2 and 3.1.3 of the Agreement.  11.2.1. The documents for the payment of the advance payment provided by the Contractor are:   * Invoice for advance payment (Annex 14) – 3 originals (one copy remains with the Customer) + 2 copies; * Declaration (notification) of the Contractor on the method of using the advance payment (Annex 15) - 3 originals (one copy remains with the Customer) + 2 copies.   11.2.2. The advance payment (with the exception of the cost of works specified in clause 3.1.1) is repaid by the Contractor by withholding funds from the amount payable to the Contractor for the works performed during the reporting period and is indicated with a minus sign in the Invoice for the works performed and the materials used and the equipment installed (Annex 3) in proportion to the amount due payment in relation to the Contract Price specified in Clause 3.1. of the Agreement.  11.2.3. In the event of termination of the Agreement before its full implementation, regardless of which party is the initiator of such termination, the outstanding part of the advance payment is returned by the Contractor in accordance with paragraph 2 of item 3 of the Procedure for the Implementation of the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit, approved by the Decree of the Cabinet of Ministers of Ukraine dated February 14, 2017 No. 73 or is repaid through mutual settlements for the completed works 10 days from the moment of termination of the Agreement.  11.3 Payments for the work performed, materials and equipment, including those imported under the terms “INCOTERMS 2010 - DAP Sheghini” are paid on the basis of the following terms and documents.  11.3.1. Payments for the execution of project works shall be made in the amount of 100 percent of the cost of performed project works on the basis of the following documents:  11.3.1.1. Payable invoice for performed works (Annex 6) signed by the Contractor and the Customer: 3 original samples (one kept by the Customer) + 2 copies;  11.3.1.2. Act of Acceptance of Performed Project Works (Author Supervision Works) (Annex 7) signed by the Contractor and the Customer: 3 original samples (one kept by the Customer) + 2 copies;  11.3.1.3. The copy of the document approving the performance of project works under the agreement between the Contractor and the designer certified by the Contractor: 3 copies of the document (one sample kept by the Customer);  11.3.1.4. In case of payment considered by clause 11.3, the following shall be additionally provided: Certificate of acceptance and transfer of technical documentation (Annex 12).  11.3.2. Payments for performance of works in terms of author supervision shall be made in the amount of 100 percent of the cost of performed works in terms of author supervision on the basis of the following documents:  11.3.2.1. Payable invoice for performed works (Annex 6) signed by the Contractor and the Customer: 3 original samples (one kept by the Customer) + 2 copies;  11.3.2.2. Act of Acceptance of Performed Project Works (Author Supervision Works) (Annex 7) signed by the Contractor and the Customer: 3 original samples (one kept by the Customer) + 2 copies.  11.3.2.3. The copy of the document approving the performance of works in terms of author supervision under the agreement between the Contractor and the owner of non-proprietary rights for the work of architecture certified by the Contractor: 3 copies of the document (one sample kept by the Customer).  11.3.3. Interim (monthly) payments for works performed, materials used and installed equipment shall be settled on basis of the following documents duly executed by the Parties:  11.3.3.1. Invoice For performed Works and Materials used and Equipment installed (Annex 3) for each part of the works performed with specification of amount due to payment signed by the Customer and Contractor - 3 originals (the Customer shall leave one for himself) + 2 copies.  The amount specified in Invoice For performed Works and Materials used and Equipment installed (Annex 3) for each part of the works performed specified in clause 10.5.1 of the Agreement shall not exceed sum 95% of the value of the work performed and 100% value of the materials used and equipment installed in the Act of Acceptance for Works and Performed Materials used and Equipment installed (Annex 9) and Certificate of Cost of Performed Works and Materials used and Equipment installed (Annex 8) for each part of construction and special installation works performed and for materials delivered and for equipment for an appropriate month.  11.3.3.2. Act of Acceptance of the Executed Construction Works (Annex 16) witch the Report on Works Execution Under the Agreement on the Site for the Period(month/year) (Annex 9) and Final Report on the Works Doun Under the Agreement on the Site for the Period (Annex 8) for each part of construction and special installation works performed and for materials delivered and for equipment for an appropriate month signed by the Contractor and the Customer - 3 originals (the Customer shall leave one for himself) + 2 copies.  11.3.3.3. Copy of multi-modal bill of lading or international consignment note of the Sender (BL, CMR, AIR WAY BILL) with the Contractor’s confirmation of the Goods delivery to a checkpoint and Package List (Annex 4), by 3 copies of consignment (the Customer shall leave one copy for himself) + 2 copies of Package List (the Customer shall leave one copy for himself);  11.3.3.4. Equipment Acceptance Protocol (Annex 5) signed by the Customer and Contractor – 3 originals (the Customer shall leave one copy for himself) + 2 copies.  11.3.4. The Final payment for works performance shall be settled on basis of the following documents duly executed by the Parties:  11.3.4.1. Invoice For performed Works and Materials used and Equipment installed (Annex 3) for each part of the works performed with specification of amount due to payment signed by the Customer and Contractor - 3 originals (the Customer shall leave one for himself) + 2 copies.  The amount specified in Invoice For performed Work sand Materials used and Equipment installed (Annex 3) for each part of the works performed specified in clause 10.5.2 of the Agreement shall constitute 5% of previously performed works value specified in the Act of Acceptance for Works Performed and Performed Materials used and Equipment installed (Annex 9) and Certificate of Cost of Performed Works and Materials used and Equipment installed (Annex 8) for each part of construction and special installation works performed and for materials delivered and for equipment for the whole period of construction works performance, but shall not exceed the difference between the amount paid and the Agreement value specified in clause 3.1 of the Agreement. The documents specified in clauses 11.3.4.2 – 11.3.4.4 Agreement, should not be presented.  11.3.4.2. Act of Acceptance of the Executed Construction Works (Annex 16) witch the Report on Works Execution Under the Agreement on the Site for the Period(month/year) (Annex 9) and Final Report on the Works Doun Under the Agreement on the Site for the Period (Annex 8) for each part of construction and special installation works performed and for materials delivered and for equipment for an appropriate month signed by the Contractor and the Customer - 3 originals (the Customer shall leave one for himself) + 2 copies;  11.3.4.3. Copy of multi-modal bill of lading or international consignment note of the Sender (BL, CMR, AIR WAY BILL) with the Contractor’s confirmation of the Goods delivery to a checkpoint and Package List (Annex 4), by 3 copies of consignment (the Customer shall leave one copy for himself) + 2 copies of Package List (the Customer shall leave one for himself);  11.3.4.4. Equipment Acceptance Protocol (Annex 5) signed by the Customer and Contractor - 3 originals (the Customer shall leave one for himself) + 2 copies.  11.3.4.5. Invoices / invoices paid by the Customer to confirm the previously received funds - 5 copies (the Customer shall one for himself).  11.3.4.6. In the case of the payment specified in clause 10.5.2 of this Agreement, the following shall be additionally submitted: Act of Works Acceptance and Delivery (Annex 10) and Act of Technical Documents Acceptance and Delivery (Annex 12) signed by the Contractor and the Customer - 3 originals (the Customer shall leave one for himself) + 2 copies.  11.4. The documents specified in clause 11.3 shall be given in two languages: in Ukrainian and in English. In case of any discrepancies in the interpretation, the English text shall prevail, excluding documents issued (executed) by the authorized bodies of Ukraine in accordance with the current legislation of Ukraine in the form where the text in Ukrainian is predominant.  11.5. Documents submitted by the Contractor in accordance with clause 11.3 (originals and copies) shall be submitted by the Contractor to the Register of the Bank and shall contain the inscription “in accordance with the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit dd. 09.09.2015”.  11.6. Upon receipt of the documents for payment, the Bank shall transfer the submitted documents to the Ministry of Finance of Ukraine which shall transmit these documents to the Customer within two days. Upon receipt of confirmation of submitted documents from the Customer, the Ministry of Finance of Ukraine shall provide the Bank with a permission to pay to the Contractor. The total period for confirmation of submitted documents may not exceed 14 days upon receipt from the Bank.  11.7. Payment by the Customer to the Contractor is the authority (permission) provided by the Ministry of Finance of Ukraine in favour of the Bank on behalf of the Customer to pay the Contractor an appropriate payment to the Contractor.  11.8. The Contractor, if the completed works are not paid after expiration of the term specified in clause 11.6 of the Agreement, may suspend the works, and shall immediately inform the Customer thereof, and in case of delay of payment for more than 45 days, the Contractor may terminate the Agreement or withdraw from the Agreement.  11.9. The Customer and the Contractor shall bear no responsibility for the actions or omission of the executive authorities of Ukraine and the Republic of Poland involved in the implementation of the Agreement in accordance with the terms and conditions of the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit dd. 09.09.2015.  **12. Warranties**  12.1. The Contractor warrants comprehensive and qualitative performance of the subject matter of the Agreement in accordance with the requirements of regulatory and technical documents, state standards of Ukraine, technical specifications and design, technical knowledge and construction science.  12.2. The Contractor provides the Customer with a warranty for the subject of the order with the following warranty terms:  12.2.1. scanning equipment - 3 years,  12.2.2. equipment of video control system - 3 years,  12.2.3. server hardware system - 3 years;  12.2.4. equipment of structured cabling system - 20 years;  12.2.5. personal computers - 3 years;  12.2.6. road surface - 3 years;  11.2.7. road signs - 2 years;  12.2.8. fencing - 3 years  12.2.9. frameworks of buildings and structures, walls, coverings and floors - 10 years;  At the same time, the terms may not be shorter than those specified in the „Information on the necessary technical, qualitative and quantitative characteristics of the procurement item”.  12.3. The date for the beginning of the warranty period is the date of commissioning of the facility, and if the final acceptance of works reveals flaws, the date for the beginning of the warranty period is the date of liquidation of the defects and deficiencies specified in the Certificate of final acceptance and extends to the period during which the facility on which the work was performed , could not be put into operation due to deficiencies within the limits of the Contractor's responsibility.  12.4. Detailed warranty conditions are provided in the warranty documents transmitted by the Contractor to the Customer at the time of final acceptance of the works.  12.5. The Contractor is responsible for defects revealed within the warranty period.  **13. Termination of the Agreement**  13.1. If the delay with the commencement, performance or completion of individual parts or the subject matter of the Agreement as a whole will last so time that it will call into question the completion of works by the Contractor within the period specified in in clause 2.1 hereof, the Customer will have the right to terminate the Agreement.  13.2. In case of poor performance of the subject of the Agreement in violation of the terms of the Agreement, the Customer may require the Contractor to change the method of works in due time. If the method of works is not changed in the established manner, the Customer may:  13.2.1. terminate the Agreement;  13.2.2. entrust the remedy of defects to another entity at the expense and at the risk of the Contractor.  13.3. Furthermore, the Customer may terminate the Agreement in the following cases:  13.3.1. submission by the creditors of an application for the Contractor's bankruptcy to the relevant court;  13.3.2. arrest of the Contractor's property by the authorized bodies for the purpose of recovery, enforcement or other disposition of the Contractor's property in order to avoid impossibility to recover the claims by creditors;  13.3.3. in cases stipulated by the current legislation of Ukraine.  13.4. The Contractor may terminate the Agreement in case of unreasonable refusal of the Customer from the acceptance of works performed hereunder and in case if the detention with payment of the performed works lasts more than 45 (forty-five) calendar days from the day of the payment obligation specified in clause 10.8. of the Agreement.  13.5. In case of termination of the Agreement by either of the parties, the Contractor is obliged immediately to stop the works performance and ensure the protection of work in progress and the construction site.  13.6. In case of termination of the Agreement by one of the parties within 14 days from the moment of delivery of the application for termination, a commission shall be appointed and an estimate of the cost of the works performed as of the date of termination shall be made, and the acceptance and transfer of the site for the works performance shall be carried out.  13.7. In case of evasion of one of the parties from the procedure described in the preceding clause, the other party shall have the right to take appropriate actions on its own, and the decisions taken by it will be considered valid.  13.8. The Parties may also terminate the Agreement on the basis of the conditions specified in paragraph 3.5 of this Agreement.  13.9. In the event of termination of the Agreement, the parties shall comply with the requirements provided for in paragraph 2, item 3 of the Procedure for the Implementation of the Agreement between the Government of Ukraine and the Government of the Republic of Poland on the provision of a loan on the terms of related aid, approved by Resolution No. 73 of the Cabinet of Ministers of Ukraine dated February 14, 2017.  **14. Contractual fines**  14.1. In case of non-fulfilment or improper fulfilment of their obligations hereunder, the Parties shall bear responsibility provided for by the legislation of Ukraine and this Agreement.  14.2. Types of violations and sanctions for them are established by the Agreement:  14.2.1. The Contractor shall bear responsibility, including for: not ensuring security on the site in accordance with the current standards when performing works.  14.2.2. The Contractor shall bear responsibility for complying with all necessary rules of sanitary and fire safety, rules of labor protection, as well as for occupational safety during the works performance and for the organization of safe passage of transport during the works performance.  14.2.3. The Parties are released from responsibility for non-fulfilment of the terms and conditions hereof if such non-fulfilment or improper fulfilment is the result of reasons beyond the control of the executing Party, such as fires, natural disasters, military actions, trade embargoes, illegal actions of third parties (hereinafter referred to as "force majeure"). In this case, the fulfilment of the terms and conditions hereof shall be postponed for a period during that such conditions will apply.  14.2.4. The Contractor shall also bear responsibility for violation of its fault of the terms of the works performance specified in p. 2.1 hereof by paying a penalty in the amount of the discount rate of the NBU valid in the period for that the penalty is calculated, from the amount of the non-fulfilled or improperly fulfilled obligation for each day of delay.  14.2.5. In case of untimely or improper fulfilment by the Parties of their other obligations under the Agreement, the guilty Party shall pay a penalty in the amount of the double discount rate of the NBU valid in the period for that the penalty is calculated, from the amount of the non-fulfilled or improperly fulfilled obligation for each day of delay.  14.2.6. Payment for losses recovery does not release the Party in breach of contractual obligations from their complete fulfilment.  14.3. The Contractor shall bear material responsibility for preserving the works performed, the consequences of their damage or destruction until the Customer accepts the works. At the moment of signing this Agreement, the Contractor shall bear material responsibility for the preservation of the constituent elements of the facility transferred to it for maintenance. In case of accidental damage of the constituent elements of the facility transferred to it for maintenance before the transfer it to the Customer, the Contractor is obliged promptly to notify the Customer thereon and immediately to eliminate the damage on its own. At the request of the Customer, the Contractor shall submit to it for approval the plan of measures for elimination of accidental damage to the facility. Upon agreement with the Customer, the Contractor may engage a third party for the elimination of damage to the facility at its own expense.  14.4. The Contractor is obliged to take measures to prevent the destruction or damage to the facility. If necessary, the Parties shall make appropriate amendments to the terms of the Agreement due to the occurrence of these circumstances.  14.5. The Contractor shall bear responsibility for compliance with the requirements of the regulatory documents for the period from the beginning of the works performance till their handover to the Customer.  14.6. In cases not provided for hereby, the Parties shall bear responsibility provided for by the current legislation of Ukraine.  **15. Force majeure**  15.1. Circumstances of force majeure are events (in particular, war, terrorist acts, catastrophes, natural disasters, riots, strikes, fires, adverse weather conditions) beyond the control of the parties and those completely or partially complicate or make impossible the works performance, substantially change the conditions of the works performance and cannot be avoided, despite taking all possible measures.  15.2. The Party referring to force majeure circumstances must confirm the fact of their occurrence.  **16. Technical supervision over the design and works performance**  16.1. Technical supervision over the design and works performance shall be carried out by the enterprise (entity) that will provide advisory services in supervision of the construction project (hereinafter referred to as the Engineer), defined on the basis of results of the open bidding conducted by the State Fiscal Service of Ukraine, (the predecessor of the State Customs Service of Ukraine), under the conditions, rights and obligations according to the Contract between the Engineer and the State Fiscal Service of Ukraine (hereinafter referred to as the Contract).  16.2. The main purpose and task for the Engineer is to assist the Customer in the management of the Agreement financed by the Government of the Republic of Poland, with due diligence and fulfillment of the Engineer's obligations stipulated in the Contract. The Engineer must perform the powers inherent to the Engineer, as specified in the Contract or inevitably derive from it, in order to ensure timely and satisfactory completion of works in accordance with the Agreement.  16.3. Provision of services by the Engineer is divided into two stages: provision of services during the design and provision of services during the construction works performance.  16.4. The Engineer's duties include the following tasks:  16.4.1. assisting the Customer in the control over the progress of design works;  16.4.2. assisting the Customer in the analysis of design decisions developed by the Contractor, for the compliance with current norms and standards of Ukraine;  16.4.3. inspection of works to verify their compliance with the specifications and drawings;  16.4.4. verification and approval of the Contractor's laboratories for carrying out control trials of materials and the works performed, issuing instructions for the elimination of improper works or those that do not comply with the standards in accordance with the current technical regulations on supervision of works in Ukraine;  16.4.5. control of the materials used in the works (including verification tests in the laboratory of the Engineer);  16.4.6. registration of daily events at the work site and the scope of works to be paid (based on the results of geometric measurements and quality checks);  16.4.7. in case of delays in the works performance in comparison with the initial or updated and approved programme of works and if it is planned to postpone the date of completion of works stipulated by the Agreement, taking all necessary measures to accelerate the works and notifying the Customer in accordance with the established procedure;  16.4.8. in case of postponement of the date of completion of works stipulated by the Agreement, defining the causes and assessment of consequences for the Agreement, reporting to the Customer on the consequences of such the postponement;  16.4.9. establishment of the content and format of monthly reports submitted by the Contractor to the Customer;  16.4.10. arranging conditional, temporary and partial acceptance of the works and the transfer of all supervision documents to the acceptance committee in accordance with the current legislation;  16.4.11. calculation of penalties, if necessary;  16.4.12. analysis and approval of the quality assurance plan submitted by the Contractor, and check of its implementation in accordance with the specification, in particular, the Engineer shall check the execution of all tests in the Contractor's laboratory according to the specified types and frequency. The Engineer shall check the quality of such tests by conducting separate (independent) tests in the laboratory of the Engineer to verify the results of the Contractor;  16.4.13. analysis of claims submitted by the Contractor and reporting whether such claims are filed in accordance with dispute settlement procedures;  16.4.14. in addition to the analysis, advising the Customer, clearly pointing out possible scenarios. The Engineer's report shall be submitted to the Customer in the form of a special report that considers a specific claim;  16.4.15. promptly reporting to the Customer of events or disputes requiring the Customer to intervene, and assistance in resolving such disputes;  16.4.16. supervision over the Contractor on all issues concerning safety and security of the works;  16.4.17. supervision over the Contractor on all issues concerning environmental protection;  16.4.18. supervision, verification and correction, if necessary, of executive drawings of the Contractor.  16.5. The Engineer's reporting to the Customer is made in accordance with the terms of the contract between the Engineer and the State Customs Service of Ukraine.  **17. Final provisions**  17.1. The provisions of the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit shall prevail over the provisions of national legislation of Ukraine that may allow the Government of Ukraine to unilaterally suspend or terminate the fulfilment of obligations hereunder until the time all obligations thereunder will be fulfilled.  17.2. This Agreement shall be agreed in accordance with the following procedure:  17.2.1. The Ministry of Finance of Ukraine shall inform in writing the Ministry of Finance of the Republic of Poland on the approval of this Agreement;  17.2.2. Thereafter, the Ministry of Finance of the Republic of Poland shall provide the Ministry of Finance of Ukraine with a written confirmation of this Agreement;  17.2.3. This Agreement will come into force within fifteen (15) days from the date of sending the written confirmation of the Ministry of Finance of the Republic of Poland to the Ministry of Finance of Ukraine and is valid until the completion of the obligations but for no longer than 5 (five) years from the date the Agreement enters into force;  17.2.4. The approval procedure for each Party shall not exceed forty-five (45) days.  17.3. The Procurement Agreement will be made public on the website of the authorized body after the written confirmation of the Ministry of Finance of the Republic of Poland to the Ministry of Finance of Ukraine.  17.4. All claims that may arise during the execution of this agreement shall be settled outside the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit dd. 09.09.2015.  17.5. All amendments, supplements and modifications to the terms and conditions hereof and annexes thereto shall be subject to the approval procedure as provided for in the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit dd. 09.09.2015, except for changes in the details of settlement accounts, about which the parties notify each other by letter.  17.6. All banking fees as well as all other possible charges that may be related to any reason regarding to payments made under the Agreement in accordance with the Agreement between the Government of Ukraine and the Government of the Republic of Poland on extending a tied aid credit dd. 09.09.2015, will be paid by each Party in its country outside the scope of this Agreement.  17.7. Possible disputes arising in the course of implementation of this Agreement are subject to resolution at the International Commercial Arbitration Court at the Chamber of Commerce and Industry of Ukraine in accordance with its Rules. The law regulating this Agreement is the substantive law of Ukraine. Venue of the Arbitration Court is the city of Kyiv (Ukraine). The language of the arbitration is Ukrainian.  17.8. When resolving issues not regulated by this Agreement, the relevant provisions of the legislation related to the implementation of the subject of the Agreement are applicable.  17.9. All amendments to the Agreement should be in writing, otherwise they will be considered invalid.  17.10. The Agreement is concluded in four identical copies in Ukrainian and English, three of those are submitted to the Customer, one to the Contractor. In case of discrepancies between the Ukrainian and English versions of the Agreement, the Ukrainian version shall prevail.  17.11. All correspondence related to this Agreement shall be in Ukrainian and English.  17.12. The parties have agreed that all correspondence related to this Agreement, sent by facsimile or by e-mail, has the force of the original.  **18. Annexes**  18.1. Annex 1: Information on necessary technical, qualitative and quantitative specifications of the procurement subject;  18.2. Annex 2: Contract Price;  18.3. Annex 2.1: Contract price for construction;  18.4. Annex 3: Invoice for the Works performed and Materials used and Equipment installed;  18.5. Annex 4: Package list for invoice;  18.6. Annex 5: Equipment Acceptance Protocol;  18.7. Annex 6: Invoice for Works Performed;  18.8. Annex 7: Act of Acceptance of Performed Project Works (Author Supervision Works);  18.9. Annex 8: Final Report on the Works Doun Under the Agreement on the Site for the Period;  18.10. Annex 9: Report on Works Execution Under the Agreement on the Site for the Period(month/year);  18.11. Annex 10: Act of Works Acceptance and Delivery;  18.12. Annex 11: Act of acceptance of the construction site;  18.13. Annex 12: Act of transfer and acceptance of technical documentation;  18.14. Annex 13: List of mechanisms, machines and equipment;  18.15. Annex 14: Invoice for advance payment;  18.16. Annex 15: Declaration (notification) of the Contractor on the method of using the advance payment.  18.17. Annex 16: Act of Acceptance of the Executed Construction Works  **19. Legal addresses and details of the parties** |
| **Замовник/ The Customer**:  **Державна митна служба України / State Customs Service of Ukraine**  Адреса/Address: Дегтярівська, 11Г , Київ, Україна, 04119 / Dehtiarivska str, 11g , Kyiv, Ukraine, 04119 /  Код ЄДРПОУ /USREOU code 43115923  т/t.+380444812042  e-mail post@customs.gov.ua  **В. о. Голови Держмитслужби / Acting Chairman of the State Customs Service of Ukraine**  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  **Сергій Звягінцев /Serhii Zviahintsev**  М.П. / Place of Seal \_\_\_\_\_\_\_\_\_\_\_\_ | **Виконавець/ The Contractor**: |